## Const Actual
[11 empty] | Prev Bal | 49266.8
[11 empty] | Transfers | 904031.95
[11 empty] | Utility | -53449.21
[8 empty] | Tax Rate |  |  | Labor | -491014.5 | [9 empty] | 2/1/2021: 2 notes. 1) Part of what Ian does is to supervise and manage what happens on the site, note he signed to receive the deliveries and verify the excavator hours. 2) He said it is now law to have toilet facilities on job sites. Ironically I heard the related ad over the weekend saying when you are renovating or constructing by law you must provide those facilities.
[8 empty] | 17.5% |  |  | Materials | -545752.2452
[8 empty] | -0.0031516 | 1994247.9052 | BDS | Funds Balance | -136917.2052 | 205705.0152 | [5 empty] | 3805.71
[7 empty] | Tax Rate | 0.175 | [9 empty] | 666 | 0.175
Date | Description | Stage | LC-Stage | Supplier | Estimate | QTY | Supplies Cost | Tax/Fees | Cost | Invoiced Amt | Posted | L/M | Supervisor | Invoice # | Delivery Type | Materials | Book # | Notes | Type Description | Type | TypDesc
2019-10-27 | - Make Copies of Plans | 2.55 | AA1 | Adrian Knight |  | 1 | 72 |  | 72 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2019-10-27 | - Structural Arrangement Drawings | 2.7 | AA1 | Adrian Knight |  | 1 | 4926 |  | 4926 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2019-10-27 | 5a. Ground Floor redesign | 2.95 | AA1 | Adrian Knight |  | 1 | 925 |  | 925 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2020-07-01 | Quantity Suveyor Report | 2.95 | AA1 | Ron Layne |  | 1 | 5600 |  | 5600 |  | Yes | L | [6 empty] | Quantity Surveyor’s Report | 2 | Architectual
2020-07-19 | Construction Drawings (Final) | 2.9 | AA1 | Adrian Knight |  | 1 | 5226 |  | 5226 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2020-09-19 | Stage 1 & 2 Final | 2.45 | AA1 | Adrian Knight |  | 1 | 4926 |  | 4926 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2020-09-19 | - Secure Town & Country Planning Approval | 2.5 | AA1 | Adrian Knight |  | 1 | 400 |  | 400 |  | Yes | L | [6 empty] | Construction Drawings Design | 2 | Architectual
2020-11-25 | Temporary water connection Fee | 10.05 | EH0 | BWA |  | 1 | 400 |  | 400 |  | Yes | M | Greg |  | SR In Store |  |  |  | Plumbing | 10 | Plumbing
2020-12-12 | Spent $85.49 yesterday on 2 pieces of 2×4 wood for the temp electricity supply and a can of marking paint | 13.05 | EH0 | Dianne |  | 1 | 85.49 |  | 85.49 | Yes | Yes | M | Greg |  | SR In Store |  |  |  | Electrical Work | 13 | Electrical
2020-12-19 | Surveyor's Land Mark Fee | 5.05 | EH0 | Michael Hutchinson |  | 1 | 900 |  | 900 |  | Yes | L | Greg |  | SR In Store |  |  |  | Site/Earthworks | 5 | Earthworks
2020-12-19 | Carters 2 Earth Rods, 3 Lugs | 13.05 | EH0 | Dianne |  | 1 | 81.65 |  | 81.65 |  | Yes | M | Greg |  | SR In Store |  |  |  | Electrical Work | 13 | Electrical
2020-12-19 | Brydens- Receipt book | 8.01 | EH0 | Brydens |  | 1 | 8.5 |  | 8.5 |  | Yes | M | Dianne | [5 empty] | Administrative | 8 | Administrative
2020-12-21 | Full set of plans at A1 size | 5.25 | EH0 | Adrian Knight |  | 1 | 288 |  | 288 |  | Yes | L | Greg |  | SR In Store |  |  |  | Make Copies of Plans | 5 | Earthworks
2020-12-22 | Clear Lot | 5.1 | EH0 | Shawn Grandison |  | 1 | 850 |  | 850 |  | Yes | L | Marlon | [5 empty] | Site/Earthworks | 5 | Earthworks
2020-12-28 | Electrical Supplies (Bok & equiptment) | 13.05 | EH0 | Ian Wiltshire | 500 | 1 | 500 |  | 500 |  | Yes | M | Greg |  | SR In Store |  |  |  | Electrical Work | 13 | Electrical
2020-12-28 | Dig hole thru rock for Electrical Pole (Anderson Fields) | 13.05 | EH0 | Modern Builders (Marlon) | 250 | 1 | 250 |  | 250 |  | Yes | L | Marlon | [5 empty] | Electrical Work | 13 | Electrical
2021-01-16 | Misc Supplies | 5.44 | EH0 | Carter & Company |  | 1 | 2348.3 | 410.95 | 2759.25 |  | Yes | M | Dianne | 8-00007138 | Delivery |  |  |  | Site/Earthworks | 5 | Earthworks
2021-01-16 | Misc Supplies | 5.44 | EH0 | Carter & Company |  | 1 | 783.38 | 137.09 | 920.47 |  | Yes | M | Dianne | 820002566 | Pick up |  |  |  | Site/Earthworks | 5 | Earthworks
2021-01-18 | Container ordered from Glassesco (First 3 Months) | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U | Dianne |  | Delivery |  |  | For Delivery today or tomorrow. | SubFloor Plant | 5 | Earthworks
2021-01-19 | BRC Steelworks purchase PO # 65123 | 5.44 | SL1 | BRC West Indies | 11564.7 | 1 | 9842.3 | 1722.4 | 11564.7 |  | Yes | M | Dianne | 65123 | Delivery | Steelwork |  | For Delivery today or Friday. | SteelWork | 5 | Earthworks
2021-01-19 | 3 Drums for Water (Beverage Express) | 8.03 | SL1 | Ian Wiltshire |  | 3 | 8 |  | 24 |  | Yes | M |  |  |  |  | 8.039 |  | Administrative | 8 | Administrative
2021-01-25 | Set out pins of the house foundations and the spot levels (1200 & 375) | 5.3 | EH0 | Michael Hutchinson |  | 1 | 1575 |  | 1575 |  | Yes | L | Greg |  | SR In Store |  |  |  | Site/Earthworks | 5 | Earthworks
2021-01-25 | Zoom Pro Subscription | 8.01 | EH0 | Zoom |  | 1 | 299.8 | 19.86 | 319.66 |  | Yes | M | Greg |  | SR In Store |  | 8.018 | Converted to BDS | Administrative | 8 | Administrative
2021-01-26 | Loads of Sand (2 meters) | 5.58 | SL1 | Shawn Grandison |  | 2 | 210 |  | 420 |  | Inv | M |  | SD020621-21 |  |  | 5.581 |  | Site/Earthworks | 5 | Earthworks
2021-01-26 | Loads of Stone (2 meters) | 5.58 | SL1 | Shawn Grandison |  | 2 | 150 |  | 300 |  | Inv | M |  | SD020621-21 |  |  | 5.5811 |  | Site/Earthworks | 5 | Earthworks
2021-01-27 | Excavation 9:30 to 3:30 | 5.42 | EH0 | Shawn Grandison |  | 6 | 180 |  | 1080 |  | Inv | L |  | SD020621-21 |  |  | 5.4211 |  | Site/Earthworks | 5 | Earthworks
2021-01-27 | Foundation & steel work | 3.01 | SL1 | Ian Wiltshire |  | 1 | 3000 |  | 3000 |  | Yes | L | Dianne |  |  |  | 3.0185 | Ian has requested a cheque for $3,000 to cover work activities through to the end of lockdown. (Approved by Greg) | Subfloor Slab | 3 | Masonary
2021-01-28 | Excavation Hammer 10:30 to 12:00 Bucket (12:00 to 4:30 | 5.42 | EH0 | Shawn Grandison |  | 6 | 180 |  | 1080 |  | Inv | L |  | SD020621-21 |  |  | 5.4211 |  | Site/Earthworks | 5 | Earthworks
2021-01-29 | Excavation 9:00 to 4:30 | 5.42 | EH0 | Shawn Grandison |  | 7.5 | 180 |  | 1350 | 4230 | Yes | L |  | SD020621-21 |  |  | 5.423 |  | Site/Earthworks | 5 | Earthworks
2021-01-29 | 3 bags Arawak Cement 94 lbs | 3.06 | SL1 | Ian Wiltshire |  | 3 | 15.27 | 8.02 | 53.83 |  | Yes | M |  | 363715 |  | Cement | 5.5895 |  | Subfloor Slab | 3 | Masonary
2021-02-15 | Barbados Light & Power - Temp Electricity | 8.04 | EH0 | BL&P |  | 1 | 370.5 |  | 370.5 | 370 | Yes | U |  |  |  |  | 8.0435 |  | Administrative | 8 | Administrative
2021-03-01 | Foundation & steel work 3/1 thru 3/19 | 3.01 | SL1 | Ian Wiltshire |  | 3 | 3000 |  | 9000 | 9000 | Yes | L |  |  |  |  | 3.0115 | Advance on wages after covid lockdown | Subfloor Slab | 3 | Masonary
2021-03-03 | 3 loads of 8" blocks - | 5.58 | SL1 | Ready Block |  | 1 | 2735.4 |  | 2735.4 | 2735 | Yes | M |  |  |  |  | 5.582 |  | Subfloor Walls | 5 | Earthworks
2021-03-03 | Misc 30 sheets, plywood, other wood, nails, marking paint etc | 5.58 | SL1 | Carter & Company |  | 1 | 2391.37 |  | 2391.37 | 2391 | Yes | M |  |  |  |  | 5.5825 |  | BASEMENT FORMWORK | 5 | Earthworks
2021-03-05 | D'Obrian Home Services(Foundation leveling) | 5.5 | EH0 | David Smith |  | 2 | 700 |  | 1400 |  | Yes | L |  |  |  |  | 5.51 | Leveling of footing and squaring of water tank | Site/Earthworks | 5 | Earthworks
2021-03-08 | Marl Compactor Rental | 5.44 | EH0 | Williams Equiptment |  | 1 | 120 | 21 | 141 |  | Yes | U |  | 856883 |  |  | 5.443 |  | Site/Earthworks | 5 | Earthworks
2021-03-10 | 34m of 3750psi concrete at 28 days @ $ 419.81 & pump for footings | 3.06 | SL2 | Ready Mix |  | 1 | 15294.4 |  | 15294.4 | 1000002580262 | Yes | M |  | 17992 |  | Concrete | 5.541 |  | Subfloor Slab | 3 | Masonary
2021-03-10 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 30000 | -93.75 | 29906.25 | 29906 | Yes | X | [6 empty] | Deposits | 1 | Transfers
2021-03-11 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 260 | 56 | 316 |  | Inv | U |  | 28589-1 |  |  |  |  | Ground Floor Plant | 8 | Administrative
2021-03-11 | Toilet Rental (initial delivery) | 8.04 | EH0 | Infra Rentals |  | 1 | 60 |  | 60 | 376 | Yes | U |  | 28589-1 |  |  | 8.0415 |  | Ground Floor Plant | 8 | Administrative
2021-03-11 | Foundation Formwork (60%) | 7.2 | SL1 | Modern Builders (Marlon) |  | 1 | 2970 |  | 2970 |  | Inv | L |  | 21031001 |  |  |  |  | FOUNDATION FORMWORK | 7 | Carpentry
2021-03-11 | Foundation Formwork (60%) | 7.2 | SL1 | Modern Builders (Marlon) |  | 1 | 1980 |  | 1980 |  | Yes | L |  | 21031001 |  |  | 7.224 |  | FOUNDATION FORMWORK | 7 | Carpentry
2021-03-11 | Setup of Electrical Supply | 13.05 | SL1 | Modern Builders (Marlon) |  | 1 | 300 |  | 300 | 3270 | Yes | L |  | 21031001 |  |  | 13.0515 |  | Electrical Work | 13 | Electrical
2021-03-12 | Load of 8" blocks | 3.11 | SL1 | Ready Block |  | 1 | 911.8 |  | 911.8 | 912 | Yes | M |  |  |  |  | 5.641 |  | Subfloor Walls | 3 | Masonary
2021-03-12 | 1 palette of Cement | 3.06 | SL1 | Carter & Company |  | 1 | 651.83 |  | 651.83 | 652 | Yes | M |  |  |  | Cement | 5.6415 |  | Subfloor Walls | 3 | Masonary
2021-03-15 | Footings pesticide treatment | 5.67 | SL1 | Greens's Exterminating & Fencing |  | 1 | 928.25 | 0 | 928.25 | 928 | Yes | M |  |  |  |  | 5.671 |  | Subfloor Slab | 5 | Earthworks
2021-03-15 | Concrete Vibrator Rental | 5.64 | SL1 | Ian Wiltshire |  | 1 | 105.75 |  | 105.75 | 106 | Yes | M |  |  |  | Tool | 5.6415 |  | Subfloor Slab | 5 | Earthworks
2021-03-16 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 70000 | -218.75 | 69781.25 | 69812 | Yes | X | [6 empty] | Deposits | 1 | Transfers
2021-03-17 | Load of 8" blocks | 3.11 | SL1 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 5.641 |  | Subfloor Walls | 3 | Masonary
2021-03-19 | Foundation & Block work work 3/19 thru 4/16 | 3.01 | SL1 | Ian Wiltshire |  | 1 | 5400 |  | 5400 |  | Inv | L |  | Ian03192021 |  |  | 3.011 |  | Subfloor Walls | 3 | Masonary
2021-03-19 | Foundation & Block work work 3/19 thru 4/16 | 3.01 | SL1 | Ian Wiltshire |  | 1 | 600 |  | 600 |  | Inv | L |  | Ian03192021 |  |  | 3.011 |  | Water Tank | 3 | Masonary
2021-03-19 | Water Tank Foundation & Block work work 3/19 thru 4/16 | 3.01 | SL1 | Ian Wiltshire |  | 1 | 3000 |  | 3000 | 12000 | Yes | L |  | Ian03192021 |  |  | 3.011 |  | Water Tank | 3 | Masonary
2021-03-19 | Foundation & Block work work 3/19 thru 4/16 | 3.01 | SL3 | Ian Wiltshire |  | 1 | 3000 |  | 3000 |  | Inv | L |  | Ian03192021 |  |  | 3.011 |  | Subfloor Slab | 3 | Masonary
2021-03-20 | Misc Supplies | 5.58 | SL1 | Carter & Company |  | 1 | 119.27 |  | 119.27 |  | Yes | M |  |  |  |  | 5.5826 |  | Subfloor Walls | 5 | Earthworks
2021-03-20 | Misc Supplies | 5.58 | SL3 | Carter & Company |  | 1 | 2778.89 |  | 2778.89 |  | Yes | M |  |  |  |  | 5.5825 |  | Subfloor Walls | 5 | Earthworks
2021-03-23 | Load of 8" blocks | 5.64 | SL3 | Ready Block |  | 2 | 911.8 |  | 1823.6 |  | Yes | M |  |  |  |  | 5.6422 |  | Subfloor Walls | 5 | Earthworks
2021-03-25 | Sand, stone & Towdown | 5.64 | SL2 | Shawn Grandison |  | 1 | 2590 |  | 2590 |  | Yes | M |  |  |  |  | 5.6424 |  | Site/Earthworks | 5 | Earthworks
2021-03-25 | Load of 8" blocks | 5.64 | SL3 | Ready Block |  | 2 | 911.8 |  | 1823.6 |  | Yes | M |  |  |  |  | 5.6423 |  | Subfloor Walls | 5 | Earthworks
2021-03-26 | 1 palette of Cement | 3.06 | SL1 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.6426 |  | Subfloor Walls | 3 | Masonary
2021-03-27 | Plumbing Supplies | 10.1 | SL1 | Carter & Company |  | 0.8 | 2692.69 |  | 2154.152 |  | Inv | M |  | 3272021 |  |  |  |  | Plumbing | 10 | Plumbing
2021-03-27 | Electrical Supplies | 13.1 | SL1 | Carter & Company |  | 0.15 | 2692.69 |  | 403.9035 |  | Inv | M |  | 3272021 |  |  |  |  | Electrical Work | 13 | Electrical
2021-03-27 | Carpentry Supplies | 5.44 | SL1 | Carter & Company |  | 0.05 | 2692.69 |  | 134.6345 | 2692.69 | Yes | M |  | 3272021 |  |  | 7.2127 |  | BASEMENT FORMWORK | 5 | Earthworks
2021-03-28 | Load of 8" blocks | 3.11 | SL3 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 5.6428 |  | Subfloor Walls | 3 | Masonary
2021-03-29 | BRC steel products (Casting for Sub Floor) | 5.44 | SL1 | BRC West Indies |  | 1 | 3522.24 |  | 3522.24 |  | Yes | M |  |  |  |  | 5.4428 |  | SteelWork | 5 | Earthworks
2021-03-31 | Foundation Formwork (4 no. foundation columns ($375/ each)) | 7.2 | SL1 | Modern Builders (Marlon) |  | 4 | 375 |  | 1500 |  | Yes | L |  |  |  |  | 7.229 |  | FOUNDATION FORMWORK | 7 | Carpentry
2021-03-31 | BWA Payment | 8.03 | SL1 | BWA |  | 1 | 64.4 |  | 64.4 |  | Yes | U |  |  |  | Utility | 8.0332 |  | Administrative | 8 | Administrative
2021-03-31 | Sub Floor Marl Infill (Bobcat infill) | 3.06 | SL2 | Shawn Grandison |  | 4 | 100 |  | 400 |  | Inv | L |  | SG0406Marl |  |  |  |  | Site/Earthworks | 3 | Masonary
2021-03-31 | Load of 8" blocks | 3.11 | SL2 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 5.6433 |  | Subfloor Walls | 3 | Masonary
2021-03-31 | Sub Floor Marl Infill | 3.06 | SL2 | Shawn Grandison |  | 9 | 390 |  | 3510 |  | Inv | M |  | SG0406Marl |  |  |  |  | Site/Earthworks | 3 | Masonary
2021-03-31 | 1 Palate Cement Cr Crds Mas (in store) | 3.06 | SL2 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.643 |  | Subfloor Walls | 3 | Masonary
2021-04-01 | Sub Floor Marl Infill (Bobcat infill) | 3.06 | SL2 | Shawn Grandison |  | 3.5 | 100 |  | 350 | 7900 | Yes | M |  | SG0406Marl |  |  | 3.0637 |  | Site/Earthworks | 3 | Masonary
2021-04-01 | 3/10/21 Additional 3m of 3750psi concrete at 28 days @ $ 419.81 & pump for footings | 3.06 | SL2 | Ready Mix |  | 3 | 419.81 | -1.5 | 1257.93 | 1000002580262 | Yes | M |  | 17992 |  | Concrete | 5.543 |  | Subfloor Slab | 3 | Masonary
2021-04-01 | Sub Floor Marl Infill | 3.06 | SL2 | Shawn Grandison |  | 6 | 390 |  | 2340 |  | Inv | M |  | SG0406Marl |  |  |  |  | Site/Earthworks | 3 | Masonary
2021-04-01 | BWA Payment | 8.03 | SL3 | BWA |  | 1 | 64.4 |  | 64.4 |  | Yes | U |  |  |  | Other | 8.0353 |  | Administrative | 8 | Administrative
2021-04-03 | Lower Well digging | 5.68 | EH0 | Anthony Seale |  | 20 | 100 |  | 2000 |  | Yes | L |  |  |  |  | 5.683 |  | Exterior Ground | 5 | Earthworks
2021-04-06 | Load of 8" blocks (Cancelled) | 5.64 | SL1 | Ready Block |  | 1 | 0 |  | 0 |  | Yes | M |  |  |  |  | 5.6431 |  | Subfloor Walls | 5 | Earthworks
2021-04-06 | Termite Treatment 1200 sq ft on 4/8/21 | 5.67 | SL2 | Greens's Exterminating & Fencing |  | 1 | 780 | 136.5 | 916.5 |  | Yes | M |  |  |  |  | 5.6738 |  | Subfloor Slab | 5 | Earthworks
2021-04-06 | Vibrating Compactor with Delivery - 1 day (Wire Xfer) | 5.64 | SL2 | Williams Equiptment |  | 1 | 141 |  | 141 |  | Yes | U |  |  |  | Tool | 5.6432 |  | Subfloor Slab | 5 | Earthworks
2021-04-07 | 1 load of 8" and 1 Load of 4" blocks | 5.64 | SL2 | Rayside Construction Ltd |  | 1 | 1904.68 |  | 1904.68 |  | Yes | M |  |  |  | Concrete | 5.6438 |  | Subfloor Walls | 5 | Earthworks
2021-04-08 | Sub Floor Concrete Slab estimate | 3.06 | SL2 | Ready Mix |  | 19 | 402.42 | 1466.34 | 9112.32 |  | Inv | M |  | 17992 |  | Concrete |  |  | Subfloor Slab | 3 | Masonary
2021-04-08 | Sub Floor Concrete Slab estimate (Placing Concrete) | 3.06 | SL2 | Ready Mix |  | 1 | 1380 |  | 1380 | 9845.42 | Yes | M |  | 17992 |  | Concrete | 3.0635 |  | Subfloor Slab | 3 | Masonary
2021-04-08 | Sub Floor Concrete Slab estimate (Pump Rental) | 3.06 | SL2 | Ready Mix |  | 1 | 500 |  | 500 |  | Inv | M |  | 17992 |  | Concrete |  |  | Subfloor Slab | 3 | Masonary
2021-04-08 | Sub Floor Concrete Slab estimate (15% Discount) | 3.06 | SL2 | Ready Mix |  | 1 | -1146.9 |  | -1146.9 |  | Inv | M |  | 17992 |  | Concrete |  |  | Subfloor Slab | 3 | Masonary
2021-04-08 | Sub Floor Sand | 3.06 | SL2 | Shawn Grandison |  | 1 | 1300 |  | 1300 |  | Inv | M |  | SG0406Marl |  |  |  |  | Site/Earthworks | 3 | Masonary
2021-04-08 | Transfer from L98 for subFloor walls | 1.11 | Xfer | Sievewright Rogers |  | 1 | 70000 | -218.75 | 69781.25 |  | Yes | X | [6 empty] | Deposits | 1 | Transfers
2021-04-09 | Contract Masonary to Sub Floor Slab level | 3.01 | SL2 | Ian Wiltshire |  | 4 | 3000 |  | 12000 |  | Yes | L |  |  |  |  | 3.0137 |  | Subfloor Slab | 3 | Masonary
2021-04-09 | Load of 8" blocks (Cancelled) | 5.64 | SL2 | Rayside Construction Ltd |  | 0 | 923.55 |  | 0 |  | Yes | M |  |  |  | other | 5.644 |  | Subfloor Walls | 5 | Earthworks
2021-04-10 | Upper Well digging (20 feet) | 5.68 | EH0 | Anthony Seale |  | 20 | 100 |  | 2000 |  | Yes | L |  |  |  | other | 5.684 |  | Exterior Ground | 5 | Earthworks
2021-04-12 | Sent in batch slips from remote transactions.. Matching invoice not located (Receivedin July) | 7.36 | FF13 | Carter & Company |  | 1 | 65.12 |  | 65.12 |  | Yes | M |  |  |  | Other | 7.3611 |  | Ground Floor Walls | 7 | Carpentry
2021-04-13 | Load of 8" blocks | 5.64 | SL3 | Ready Block |  | 2 | 911.8 |  | 1823.6 |  | Yes | M |  |  |  | other | 5.6441 |  | Subfloor Walls | 5 | Earthworks
2021-04-14 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  | other | 8.0443 |  | Ground Floor Plant | 8 | Administrative
2021-04-14 | Basement Slab Formwork | 7.21 | SL2 | Modern Builders (Marlon) |  | 1 | 670 |  | 670 |  | Inv | L |  | 21041401 |  | other |  |  | BASEMENT FORMWORK | 7 | Carpentry
2021-04-14 | First Electrical Installation (Basement) | 13.1 | SL3 | Modern Builders (Marlon) |  | 1 | 1850 |  | 1850 |  | Inv | L |  | 21041401 |  | other |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2021-04-14 | Load of 8" blocks | 3.11 | SL3 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  | other | 5.6441 |  | Subfloor Walls | 3 | Masonary
2021-04-14 | First Plumbing Installation (Hot, Cold water & Waste | 10.3 | SL3 | Modern Builders (Marlon) |  | 1 | 1630 |  | 1630 | 4150 | Yes | L |  | 21041401 |  | other | 10.3425 |  | Plumbing | 10 | Plumbing
2021-04-14 | 1 Load of Cement | 3.06 | SL3 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.6443 |  | Subfloor Walls | 3 | Masonary
2021-04-16 | Sub Floor Concrete Slab estimate (refund) -52.23 | 3.06 | SL2 | Ready Mix |  | 1 | -1257.93 |  | -1257.93 |  | Yes | M |  | 17992 |  | Concrete | 3.0657 |  | Subfloor Slab | 3 | Masonary
2021-04-18 | Container ordered from Glassesco (Second 3 Months) | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U | Dianne |  |  | other | 5.4444 | Renewal | SubFloor Plant | 5 | Earthworks
2021-04-18 | 3 Cans of Marking Paint & metal cutting disc | 3.1 | SL3 | Carter & Company |  | 1 | 51.45 |  | 51.45 |  | Yes | M |  |  |  | other | 3.1445 |  | Ground Floor Slab | 3 | Masonary
2021-04-19 | Load of 8" blocks | 3.11 | SL3 | Ready Block |  | 3 | 911.8 |  | 2735.4 |  | Yes | M |  |  |  | other | 3.1145 |  | Subfloor Walls | 3 | Masonary
2021-04-19 | Scaffold Rentals for Two weeks | 3.1 | SL3 | Tucker Johnston |  | 1 | 240 |  | 240 |  | Yes | U |  |  |  | other | 3.145 |  | SubFloor Plant | 3 | Masonary
2021-04-21 | 1 Palate Cement | 3.06 | SL3 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.6446 |  | Subfloor Walls | 3 | Masonary
2021-04-21 | Misc (Steel, Nails, Concrete waterproofer) | 5.64 | SL3 | Carter & Company |  | 1 | 312.51 |  | 312.51 |  | Yes | M |  |  |  | Other | 5.6447 |  | Exterior Ground | 5 | Earthworks
2021-04-24 | BRC Steelworks purchase PO # XXXX | 5.44 | SL1 | BRC West Indies |  | 1 | 5076.41 | 888.37 | 5964.78 |  | Yes | M | Dianne |  | Delivery | Other | 5.4449 | For Delivery today or Friday. | SteelWork | 5 | Earthworks
2021-04-24 | Misc Masonary for water proofing | 3.06 | SL2 | Carter & Company |  | 1 | 304.3 |  | 304.3 | 10604.3 | Yes | M |  | CTRS0426 | Delivery | Other | 3.0648 |  | Exterior Ground | 3 | Masonary
2021-04-24 | Props for boxing Ground Floor (50) | 7.3 | SL3 | Williams Equiptment |  | 1 | 739.2 |  | 739.2 |  | Yes | U |  |  |  | Other | 7.3495 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-04-24 | Misc Plumbing Supplies | 10.2 | SL4 | Carter & Company |  | 1 | 5150 |  | 5150 |  | Inv | M |  | CTRS0426 | Delivery | Other |  |  | Plumbing | 10 | Plumbing
2021-04-24 | Misc ElectricalSupplies | 13.2 | SL4 | Carter & Company |  | 1 | 2575 |  | 2575 |  | Inv | M |  | CTRS0426 | Delivery | Other |  |  | Electrical Work | 13 | Electrical
2021-04-24 | Misc Carpentry Supplies | 7.3 | SL4 | Carter & Company |  | 1 | 2575 |  | 2575 |  | Inv | M |  | CTRS0426 | Delivery | Other |  |  | Subfloor Slab | 7 | Carpentry
2021-04-26 | Load of 8" blocks | 3.11 | SL3 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  | Other | 3.1151 |  | Subfloor Walls | 3 | Masonary
2021-04-26 | Barbados Light & Power | 8.04 | SL3 | BL&P |  | 1 | 86.77 |  | 86.77 |  | Yes | U |  |  |  | Other | 8.045 |  | Administrative | 8 | Administrative
2021-04-26 | 30 Exterior Plywood sheets | 7.3 | SL4 | Barbados Lumber Company -Delivery |  | 30 | 58.74 | 328.3 | 2090.5 |  | Yes | M |  | CTRS0426 | Delivery | Other | 7.35 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-04-30 | BRC 5 sq stirrups | 5.44 | SL1 | BRC West Indies |  | 1 | 111.04 |  | 111.04 |  | Yes | M | Dianne |  | Delivery | Other | 5.4452 |  | Subfloor Walls | 5 | Earthworks
2021-04-30 | Misc Masonary (Ian receipts ) | 3.06 | SL2 | Charles Rowe Bridge Discount Hardware |  | 1 | 733.68 |  | 733.68 |  | Yes | M |  |  | Pickup | Other | 3.0652 |  | Subfloor Walls | 3 | Masonary
2021-04-30 | 8 bags of Cement (Charles Rowe Bridge Hardware) | 3.01 | SL3 | Ian Wiltshire |  | 2 | 61.08 | 21.38 | 143.54 |  | Yes | M |  |  |  | Cement | 3.0157 |  | Subfloor Walls | 3 | Masonary
2021-04-30 | 1 Palate Cement | 3.06 | SL3 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.6452 |  | Subfloor Walls | 3 | Masonary
2021-05-01 | Building Start Certificate | 8.03 | EH0 | Town & Country Planning |  | 1 | 100 |  | 100 |  | Yes | M |  |  |  | Other | 8.0353 |  | Administrative | 8 | Administrative
2021-05-06 | Bond beam formwork (alternative solution for 12" foundation walls | 7.21 | GL6 | Modern Builders (Marlon) |  | 1 | 175 |  | 175 |  | Inv | L |  | 21050601 |  | Other |  |  | BASEMENT FORMWORK | 7 | Carpentry
2021-05-06 | steel/BRC mesh, metal cutting Discs | 5.64 | GL6 | Carter & Company |  | 1 | 1024.69 |  | 1024.69 |  | Yes | M |  |  |  | Cement | 5.6454 |  | Ground Floor Slab | 5 | Earthworks
2021-05-06 | Previous payment received for Basement slab formwork | 7.21 | SL2 | Modern Builders (Marlon) |  | 1 | -670 |  | -670 | 4698 | Yes | L |  | 21050601 |  | Other | 7.2156 |  | BASEMENT FORMWORK | 7 | Carpentry
2021-05-06 | Formwork for Basement level Formwork (45 % complete) | 7.21 | SL3 | Modern Builders (Marlon) |  | 1 | 5193 |  | 5193 |  | Inv | L |  | 21050601 |  | Sub FLOOR FORMWORK |  |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-05-07 | 60 Exterior Plywood sheets | 7.3 | GL6 | Marshall's Trading |  | 60 | 85 | -0.03 | 5099.97 |  | Yes | M |  |  | Delivery | Other | 7.356 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-05-07 | Sand and Stone | 3.06 | SL2 | Shawn Grandison |  | 1 | 2660 |  | 2660 | 13890 | Yes | M |  | 74 |  | Other | 3.066 |  | Site/Earthworks | 3 | Masonary
2021-05-07 | Bob Cat Work for ground floor foundation /Slab | 5.45 | SL2 | Shawn Grandison |  | 1 | 700 |  | 700 |  | Inv | M |  | 74 |  | Other |  |  | Site/Earthworks | 5 | Earthworks
2021-05-07 | Marl Fill | 5.45 | SL3 | Shawn Grandison |  | 1 | 10530 |  | 10530 |  | Inv | M |  | 74 |  | Other |  |  | Site/Earthworks | 5 | Earthworks
2021-05-08 | Earthworks ( Excavatio) | 5.42 | EH0 | Shawn Grandison |  | 6 | 170 |  | 1020 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-08 | Earthworks (Bobca) | 5.42 | EH0 | Shawn Grandison |  | 7 | 100 |  | 700 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-10 | Earthworks ( Excavatio) | 5.42 | EH0 | Shawn Grandison |  | 6.5 | 170 |  | 1105 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-10 | Earthworks (Bobca) | 5.42 | EH0 | Shawn Grandison |  | 6.5 | 100 |  | 650 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-10 | Props for boxing Ground Floor (102) | 7.3 | GL6 | Williams Equiptment |  | 1 | 1555.7 |  | 1555.7 | 1699.24 | Yes | U |  |  |  | Other | 7.3575 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-05-10 | Cast Iron cover for water tank | 3.06 | GL6 | Williams Equiptment |  | 1 | 622.75 |  | 622.75 |  | Yes | M |  |  |  | Other | 3.0659 |  | Water Tank | 3 | Masonary
2021-05-10 | Reordered Pine, Ad Mix & Mortar Bond | 7.3 | GL6 | Marshall's Trading |  | 1 | 427.17 |  | 427.17 |  | Yes | M |  |  |  | Other | 7.3585 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-05-11 | Earthworks ( Excavatio) | 5.42 | EH0 | Shawn Grandison |  | 7.5 | 170 |  | 1275 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-11 | Earthworks (Bobca) | 5.42 | EH0 | Shawn Grandison |  | 7.5 | 100 |  | 750 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-11 | Barbados Light & Power - Temp Electricity | 8.04 | EH0 | BL&P | 1 | 1 | 13.38 |  | 13.38 |  | Yes | U |  |  |  | other | 8.0475 |  | Administrative | 8 | Administrative
2021-05-12 | Earthworks Load of Sand | 5.42 | EH0 | Shawn Grandison |  | 1 | 1300 |  | 1300 |  | Inv | M |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-12 | Earthworks Load of stonel) | 5.42 | EH0 | Shawn Grandison |  | 1 | 950 |  | 950 |  | Inv | M |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-12 | Earthworks ( Excavatio) | 5.42 | EH0 | Shawn Grandison |  | 2 | 170 |  | 340 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-12 | Earthworks (Bobca) | 5.42 | EH0 | Shawn Grandison |  | 2 | 100 |  | 200 |  | Inv | L |  | 05182021-80 |  |  |  |  | Site/Earthworks | 5 | Earthworks
2021-05-12 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  | other | 8.0462 |  | Ground Floor Plant | 8 | Administrative
2021-05-12 | Load of 8" blocks | 3.11 | GL6 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  | Other | 3.1161 |  | Ground Floor Walls | 3 | Masonary
2021-05-12 | Termite Treatment | 5.67 | GL6 | Greens's Exterminating & Fencing |  | 1 | 916.5 |  | 916.5 |  | Yes | M |  |  |  | other | 5.6762 |  | Ground Floor Slab | 5 | Earthworks
2021-05-12 | 1 Palate Cement | 3.06 | GL6 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 5.646 |  | Ground Floor Walls | 3 | Masonary
2021-05-12 | Masonary Services | 3.26 | GL8 | Ian Wiltshire |  | 1 | 1800 |  | 1800 |  | Yes | L |  | Ian05122021 |  | other | 3.2662 |  | Foundation Extras Work | 3 | Masonary
2021-05-12 | Masonary Services | 3.26 | GL8 | Ian Wiltshire |  | 1 | 9800 |  | 9800 |  | Yes | L |  | Ian05122021 |  | other | 3.2662 |  | Ground Floor Walls | 3 | Masonary
2021-05-12 | Masonary Services | 3.26 | GL8 | Ian Wiltshire |  | 1 | 1000 |  | 1000 |  | Yes | L |  | Ian05122021 |  | other | 3.2662 |  | Plaster | 3 | Masonary
2021-05-12 | Masonary Services | 3.26 | GL8 | Ian Wiltshire |  | 1 | 400 |  | 400 |  | Yes | L |  | Ian05122021 |  | other | 3.2662 |  | Subfloor Slab | 3 | Masonary
2021-05-12 | Masonary Services | 3.26 | GL8 | Ian Wiltshire |  | 1 | 1000 |  | 1000 | 14000 | Yes | L |  | Ian05122021 |  | other | 3.2662 |  | Subfloor Slab | 3 | Masonary
2021-05-13 | Formwork for Basement level (70 % complete) | 7.22 | GL6 | Modern Builders (Marlon) |  | 1 | 2885 |  | 2885 |  | Yes | L |  |  |  | other | 7.2289 |  | BASEMENT FORMWORK | 7 | Carpentry
2021-05-13 | Cement Mixer Rental | 3.1 | GL6 | Brian Hinds |  | 2 | 1233.75 |  | 2467.5 |  | Yes | M |  |  |  | other | 3.1635 |  | Ground Floor Walls | 3 | Masonary
2021-05-13 | Vibrating Compactor with Delivery - 2 days(Wire Xfer) | 5.64 | GL6 | Williams Equiptment | 1 | 1 | 180 | 36.75 | 216.75 |  | Yes | U |  |  |  |  | 5.6471 |  | Ground Floor Slab | 5 | Earthworks
2021-05-13 | Scaffold Rentals for one extra week | 3.1 | GL6 | Tucker Johnston | 1 | 1 | 90 |  | 90 |  | Yes | U |  |  |  | other | 3.163 |  | Ground Floor Plant | 3 | Masonary
2021-05-13 | Vibrating Compactor Delivery -(Transportation) | 5.64 | GL6 | Williams Equiptment | 1 | 1 | 30 |  | 30 |  | Yes | U |  |  |  |  | 5.6472 |  | Ground Floor Slab | 5 | Earthworks
2021-05-13 | Plumbing Supplies | 10.2 | GL6 | Carter & Company |  | 1 | 1028.75 |  | 1028.75 |  | Yes | M |  |  |  | other | 10.264 |  | Plumbing | 10 | Plumbing
2021-05-15 | Ian-Scaffold Refund | 3.26 | GL8 | Ian Wiltshire |  | 1 | 330 |  | 330 |  | Yes | U |  |  |  |  | 3.261 |  | Roof Plant | 3 | Masonary
2021-05-17 | Load of 8" blocks | 3.11 | GL6 | Ready Block |  | 3 | 911.8 |  | 2735.4 |  | Yes | M |  | 387985 |  | other | 3.1164 |  | Ground Floor Slab | 3 | Masonary
2021-05-17 | Load of 4" blocks | 3.11 | GL6 | Ready Block |  | 1 | 1144.45 |  | 1144.45 |  | Yes | M |  | 387985 |  | other | 3.1165 |  | Ground Floor Walls | 3 | Masonary
2021-05-17 | Cement & Steel | 3.06 | GL6 | Carter & Company |  | 1 | 3250.64 |  | 3250.64 |  | Yes | M |  |  |  | Cement | 3.0666 |  | Ground Floor Slab | 3 | Masonary
2021-05-18 | Earthworks (Marlfill) | 5.42 | EH0 | Shawn Grandison |  | 1 | 390 |  | 390 | 8680 | Yes | M |  | 05182021-80 |  |  | 5.4272 |  | Site/Earthworks | 5 | Earthworks
2021-05-21 | Partial Formwork for Basement level (90 % complete) | 7.22 | GL6 | Modern Builders (Marlon) |  | 1 | 2308 |  | 2308 |  | Yes | L |  | 21052001 |  |  | 7.2272 |  | BASEMENT FORMWORK | 7 | Carpentry
2021-05-21 | Reimbursment to Electrician for Purchase of parts | 13.3 | GL6 | Modern Builders (Marlon) |  | 1 | 51.29 | 8.98 | 60.27 |  | Yes | M | Marlon |  |  | Other | 13.385 |  | Ground Floor Walls | 13 | Electrical
2021-05-21 | First fix plumbing installation (Hot, cold water & waste) -Ground Floor | 10.34 | GL6 | Modern Builders (Marlon) |  | 1 | 2430 |  | 2430 |  | Yes | L |  | 21052001 |  |  | 10.3473 |  | Plumbing | 10 | Plumbing
2021-05-21 | Installation of rain water pipework (30% complete) | 10.34 | GL6 | Modern Builders (Marlon) |  | 1 | 525 |  | 525 |  | Yes | L |  | 21052001 |  |  | 10.3474 |  | Plumbing | 10 | Plumbing
2021-05-24 | Reimbursment to Electrician for Purchase of parts (10% discount) | 13.3 | GL6 | Modern Builders (Marlon) |  | 1 | 180.279 | 31.55 | 211.829 |  | Yes | M | Marlon | 342012 |  | Other | 13.3855 |  | Ground Floor Walls | 13 | Electrical
2021-05-25 | 34m of 3750psi concrete at 28 days @ $ 419.81 & pump for Ground Floor | 3.06 | GL6 | Ready Mix |  | 1 | 18901.27 |  | 18901.27 |  | Yes | M |  | 18287 |  | Concrete | 3.0665 |  | Ground Floor Slab | 3 | Masonary
2021-05-25 | Actual Concrete difference (34m of 3750psi concrete at 28 days @ $ 419.81 & pump for Ground Floor) | 3.06 | GL6 | Ready Mix |  | 1 | 4245.17 |  | 4245.17 |  | Yes | M |  | 18287 |  | Concrete | 3.0678 |  | Ground Floor Slab | 3 | Masonary
2021-05-26 | Load of 8" blocks | 3.11 | GL6 | Ready Block |  | 3 | 911.8 |  | 2735.4 |  | Yes | M |  | 526367540 |  | other | 3.1174 |  | Ground Floor Walls | 3 | Masonary
2021-05-26 | Load of 6" blocks | 3.11 | GL6 | Ready Block |  | 1 | 940 |  | 940 |  | Yes | M |  | 526367540 |  | other | 3.1174 |  | Ground Floor Walls | 3 | Masonary
2021-05-26 | Marking Paint & nails | 3.11 | GL6 | Carter & Company |  | 1 | 52.22 |  | 52.22 |  | Yes | M |  |  |  | other | 3.1175 |  | Ground Floor Walls | 3 | Masonary
2021-05-27 | Purchase of Electrical Boxes | 13.3 | SL4 | Dianne |  | 1 | 42.79 |  | 42.79 |  | Yes | M |  |  |  | other | 13.382 |  | Subfloor Walls | 13 | Electrical
2021-05-28 | First fix electrical installation -Ground Floor | 13.3 | GL6 | Modern Builders (Marlon) |  | 1 | 2040 |  | 2040 |  | Inv | L |  | 21052701 |  | other |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2021-05-28 | Formwork for Basement level (90 % complete) | 7.21 | SL3 | Modern Builders (Marlon) |  | 1 | 1154 |  | 1154 | 3794 | Yes | L |  | 21052701 |  | other | 7.2177 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-05-28 | Electrical conduit extensions - Basement Level | 13.3 | SL4 | Modern Builders (Marlon) |  | 1 | 600 |  | 600 |  | Inv | L |  | 21052701 |  | other |  |  | Electrical Work (Conduit extensions) | 13 | Electrical
2021-06-01 | Scaffolding Rentals | 3.16 | GL6 | Williams Equiptment |  | 12 | 7 |  | 84 |  | Inv | U |  | 8368258 |  | other |  |  | Ground Floor Plant | 3 | Masonary
2021-06-01 | Scaffolding Rentals | 3.16 | GL6 | Williams Equiptment |  | 12 | 14 |  | 168 |  | Inv | U |  | 8368258 |  | other |  |  | Ground Floor Plant | 3 | Masonary
2021-06-01 | Scaffolding Rentals | 3.16 | GL6 | Williams Equiptment |  | 6 | 28 |  | 168 |  | Inv | U |  | 8368258 |  | other |  |  | Ground Floor Plant | 3 | Masonary
2021-06-01 | Transportation | 3.16 | GL6 | Williams Equiptment |  | 1 | 60 |  | 60 |  | Inv | U |  | 8368258 |  | other |  |  | Ground Floor Walls | 3 | Masonary
2021-06-01 | Vat | 3.16 | GL6 | Williams Equiptment |  | 1 | 84 |  | 84 | 564 | Yes | M |  | 8368258 |  | other | 3.168 |  | Ground Floor Walls | 3 | Masonary
2021-06-01 | Steel | 3.16 | GL6 | Carter & Company |  | 1 | 2898.43 |  | 2898.43 |  | Inv | M |  | 3550260601 |  | other |  |  | Ground Floor Walls | 3 | Masonary
2021-06-01 | Cement | 3.16 | GL6 | Carter & Company |  | 1 | 651.83 |  | 651.83 | 3550.26 | Yes | M |  | 3550260601 |  | Cement | 3.1681 |  | Ground Floor Walls | 3 | Masonary
2021-06-03 | Transfer from L98/(IRRA) | 1.11 | Xfer | Sievewright Rogers | 1 | 1 | 90000 | -281.25 | 89718.75 |  | Yes | X |  |  |  | other |  |  | Deposits | 1 | Transfers
2021-06-05 | Masonary Services | 3.26 | GL6 | Ian Wiltshire |  | 1 | 2000 |  | 2000 |  | Yes | L | Ian | Ian06052021 |  | Other | 3.2684 |  | First Floor Walls | 3 | Masonary
2021-06-05 | Masonary Services | 3.26 | GL6 | Ian Wiltshire |  | 1 | 6500 |  | 6500 |  | Yes | L | Ian | Ian06052021 |  | Other | 3.2684 |  | Ground Floor Slab | 3 | Masonary
2021-06-05 | Masonary Services | 3.26 | GL6 | Ian Wiltshire |  | 1 | 1500 |  | 1500 | 10000 | Yes | L | Ian | Ian06052021 |  | Other | 3.2684 |  | Subfloor Slab | 3 | Masonary
2021-06-05 | misc Masonary Items | 3.16 | GL6 | Carter & Company |  | 1 | 122.52 |  | 122.52 |  | Yes | M | Ian |  |  | Other | 3.1684 |  | Ground Floor Walls | 3 | Masonary
2021-06-07 | Second Container | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U | Dianne |  |  | other | 5.4482 |  | SubFloor Plant | 5 | Earthworks
2021-06-07 | BRC Order Ticket # 511024 | 3.21 | FF12 | BRC West Indies |  | 1 | 3875.49 |  | 3875.49 |  | Yes | M |  |  |  | other | 3.2189 |  | First Floor Slab | 3 | Masonary
2021-06-07 | Props for boxing Ground Floor (132) thru 6/15 | 7.3 | GL6 | Williams Equiptment |  | 1 | 1037.4 |  | 1037.4 |  | Yes | U |  |  |  | other | 7.383 |  | Ground Floor Slab | 7 | Carpentry
2021-06-07 | misc Masonary Items | 3.16 | GL6 | Ian Wiltshire |  | 1 | 2219.5 |  | 2219.5 |  | Yes | M | Ian |  |  | Other | 3.1686 |  | Ground Floor Walls | 3 | Masonary
2021-06-07 | Misc plumbing items (piping) | 10.34 | GL6 | Modern Builders (Marlon) |  | 1 | 445.14 |  | 445.14 |  | Yes | M | Marlon |  |  | Other | 10.3487 |  | Plumbing | 10 | Plumbing
2021-06-07 | Refund (Diesel $50, Therminex $26.65, Conduit, bends..$211.83) | 3.16 | GL6 | Ian Wiltshire |  | 1 | 288.48 |  | 288.48 |  | Yes | M |  |  |  | other | 3.1689 |  | Ground Floor Walls | 3 | Masonary
2021-06-09 | Roofing Lumber (pre Ordered) | 7.5 | FF14 | Carter & Company |  | 1 | 15401.42 |  | 15401.42 |  | Yes | M |  |  |  | other | 7.588 |  | Roof Construction | 7 | Carpentry
2021-06-11 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  | other | 8.0488 |  | Ground Floor Plant | 8 | Administrative
2021-06-11 | 3 loads 8" Blocks ordered. $2,735.40 | 3.11 | GL6 | Ready Block |  | 3 | 911.8 |  | 2735.4 |  | Yes | M |  |  |  | other | 3.1187 |  | Ground Floor Walls | 3 | Masonary
2021-06-15 | Bank Transfer - Lumber Pieces not obtained from Carters | 7.5 | FF14 | LG Lumber |  | 1 | 2155.7 |  | 2155.7 |  | Yes | M |  |  |  | Other | 7.5905 |  | Roof Construction | 7 | Carpentry
2021-06-15 | Difference on exchanged lumber on 9-Jun transaction plus Waste Pipes, cement, deal board, pine | 7.5 | FF14 | Carter & Company |  | 1 | 2512.81 |  | 2512.81 |  | Yes | M |  |  |  | Other | 7.5895 |  | Roof Construction | 7 | Carpentry
2021-06-15 | Bank Transfer - 50lb quantities of nails | 7.3 | GL6 | Marshall's Trading |  | 1 | 809.29 |  | 809.29 |  | Yes | M |  |  |  | Other | 7.3915 |  | First Floor Slab | 7 | Carpentry
2021-06-15 | Mixer Period Between 12-May and 11-Jun. 2 weeks 29-May to 11-Jun | 3.1 | GL6 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | M |  |  |  | Other | 3.191 |  | Ground Floor Walls | 3 | Masonary
2021-06-15 | 1Extra length waste pipe | 10.34 | GL6 | Carter & Company |  | 1 | 72.71 |  | 72.71 |  | Yes | M |  |  |  | Other | 10.349 |  | Ground Floor Walls | 10 | Plumbing
2021-06-16 | Electricity | 8.04 | SL3 | BL&P |  | 1 | 17.93 |  | 17.93 |  | Yes | U |  |  |  | Other | 8.0492 |  | Administrative | 8 | Administrative
2021-06-19 | Yard Broom | 7.36 | FF13 | Carter & Company |  | 1 | 18.84 |  | 18.84 |  | Yes | M |  |  |  | other | 7.3611 |  | Ground Floor Walls | 7 | Carpentry
2021-06-22 | BWA Payment | 8.03 | SL3 | BWA |  | 1 | 249.65 |  | 249.65 |  | Yes | U |  |  |  | Other | 8.0311 |  | Administrative | 8 | Administrative
2021-06-23 | Plumbing Supplies | 10.2 | GL7 | Carter & Company |  | 1 | 1922.04 | 336.36 | 2258.4 |  | Yes | M |  |  |  | Other | 10.296 |  | Ground Floor Walls | 10 | Plumbing
2021-06-23 | Scaffold Extension | 7.36 | GL8 | Williams Equiptment |  | 1 | 581.63 |  | 581.63 |  | Yes | U |  |  |  | Other | 7.3696 |  | First Floor Plant | 7 | Carpentry
2021-06-23 | 1 Load of Cement | 3.16 | GL8 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 3.1696 |  | Ground Floor Walls | 3 | Masonary
2021-06-24 | Formwork for Ground floor level (25 % complete) | 7.22 | GL7 | Modern Builders (Marlon) |  | 1 | 3557.5 |  | 3557.5 |  | Inv | L |  | 21062401 |  | Other |  |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-06-24 | Rain water pipework (50 % complete) | 10.35 | GL7 | Modern Builders (Marlon) |  | 1 | 875 |  | 875 | 4432.5 | Yes | L |  | 21062401 |  | Other | 10.3595 |  | Plumbing | 10 | Plumbing
2021-06-26 | Architectual changes inclusive of the town planning revised drawing fee | 5.25 | EH0 | Adrian Knight |  | 1 | 450 |  | 450 |  | Yes | L |  |  |  | Other | 5.2593 |  | Secure Town & Country Planning Approval | 5 | Earthworks
2021-06-26 | Formply for formwork | 7.36 | GL7 | Marshall's Trading |  | 1 | 1699.99 |  | 1699.99 |  | Yes | M |  |  |  | Other | 7.3694 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-06-29 | Earthworks (sande, Stone, Bobcat work & Marlfill | 5.42 | EH0 | Shawn Grandison |  | 1 | 4020 |  | 4020 |  | Yes | L |  |  |  | Other | 5.4294 |  | Site/Earthworks | 5 | Earthworks
2021-07-01 | Formwork for Ground floor level (60 % complete) | 7.22 | GL7 | Modern Builders (Marlon) |  | 1 | 4980.5 |  | 4980.5 |  | Yes | L |  |  |  | Other | 7.2293 |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-07-03 | Plate compactor (1 day) | 5.64 | EH0 | Williams Equiptment |  | 1 | 141 |  | 141 |  | Yes | U |  |  |  |  | 5.6498 |  | Exterior Ground | 5 | Earthworks
2021-07-03 | 24 plywood sheets | 7.36 | FF12 | Marshall's Trading |  | 1 | 2039.99 |  | 2039.99 |  | Yes | M |  |  |  |  | 7.3697 |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2021-07-03 | 4 loads 8" block | 3.46 | FF13 | Ready Block |  | 1 | 3647.2 |  | 3647.2 |  | Yes | M |  |  |  |  | 3.4698 |  | First Floor Walls | 3 | Masonary
2021-07-08 | STEEL HT 1/2i 12MMx6MT | 3.46 | FF12 | Carter & Company |  | 1 | 2546.61 | 445.66 | 2992.27 |  | Yes | M |  |  |  | Steelwork | 3.4697 |  | First Floor Slab | 3 | Masonary
2021-07-08 | Electrical conduit Extensions - Ground floor level | 13.37 | GL7 | Modern Builders (Marlon) |  | 1 | 720 |  | 720 | 3566 | Yes | L |  | 21070801 |  |  | 13.3799 |  | Electrical Work (Conduit extensions) | 13 | Electrical
2021-07-08 | Formwork for Ground floor level (80 % complete) | 7.22 | GL7 | Modern Builders (Marlon) |  | 1 | 2846 |  | 2846 |  | Inv | L |  | 21070801 |  |  |  |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-07-08 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 80000 | -250 | 79750 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2021-07-09 | 38m of 3750psi concrete at 28 days @ $ 419.81 & pump for Ground Floor | 3.6 | FF12 | Ready Mix | 19540.09 | 1 | 19540.09 |  | 19540.09 |  | Yes | M |  |  |  | Concrete | 3.6101 |  | First Floor Slab | 3 | Masonary
2021-07-09 | Masonary Services | 3.26 | FF12 | Ian Wiltshire |  | 1 | 10900 |  | 10900 |  | Yes | L |  | Ian070921 |  | Other | 3.261 |  | First Floor Slab | 3 | Masonary
2021-07-09 | Masonary Services | 3.26 | FF12 | Ian Wiltshire |  | 1 | 4100 |  | 4100 | 15000 | Yes | L |  | Ian070921 |  | Other | 3.261 |  | Subfloor Slab | 3 | Masonary
2021-07-09 | Concrete Cutting Disc | 3.26 | FF12 | Dianne |  | 1 | 62.99 |  | 62.99 |  | Yes | M |  |  |  | Other | 3.261 |  | First Floor Slab | 3 | Masonary
2021-07-09 | Epoxy for connecting steel to concrete and metal cutting disc for cutting the steel. | 3.26 | FF12 | Carter & Company |  | 1 | 127.9 |  | 127.9 |  | Yes | M |  |  |  | Other | 3.261 |  | First Floor Slab | 3 | Masonary
2021-07-13 | 150 props for 3 weeks | 3.26 | FF12 | Stephen Carter |  | 1 | 1125 |  | 1125 |  | Yes | M |  |  |  |  | 3.261 |  | First Floor Slab | 3 | Masonary
2021-07-13 | Carter's cement ordered 13-Jul | 3.26 | SL4 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 3.261 |  | First Floor Walls | 3 | Masonary
2021-07-18 | Container ordered from Glassesco (Second 3 Months) | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U |  |  |  |  | 5.4411 |  | SubFloor Plant | 5 | Earthworks
2021-07-18 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  |  | 8.0411 |  | Ground Floor Plant | 8 | Administrative
2021-07-18 | Props Extention 30 | 7.36 | FF12 | Williams Equiptment |  | 1 | 528.75 |  | 528.75 |  | Yes | U |  |  |  |  | 7.3611 |  | First Floor Slab | 7 | Carpentry
2021-07-19 | First fix electrical installation - First Floor | 13.38 | FF13 | Modern Builders (Marlon) |  | 1 | 2040 |  | 2040 |  | Inv | L |  | 21071901 |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2021-07-19 | First fix plumbing installation (Hot, cold water & waste) - First Floor | 10.38 | FF13 | Modern Builders (Marlon) |  | 1 | 2430 |  | 2430 |  | Inv | L |  | 21071901 |  |  |  |  | Plumbing | 10 | Plumbing
2021-07-19 | Load of 8" blocks | 7.36 | FF13 | Ready Block |  | 2 | 911.8 |  | 1823.6 |  | Yes | M |  |  |  |  | 7.3611 |  | First Floor Walls | 7 | Carpentry
2021-07-19 | Load of 4" blocks | 7.36 | FF13 | Ready Block |  | 1 | 1144.45 |  | 1144.45 |  | Yes | M |  |  |  |  | 7.3611 |  | First Floor Walls | 7 | Carpentry
2021-07-19 | Installation of rain water pipework (60% complete) | 10.38 | FF13 | Modern Builders (Marlon) |  | 1 | 525 |  | 525 | 7841 | Yes | L |  | 21071901 |  |  | 10.3811 |  | Plumbing | 10 | Plumbing
2021-07-19 | 1 Ton Steel and wheel barrow | 7.36 | FF13 | Carter & Company |  | 1 | 3213.43 |  | 3213.43 |  | Yes | M |  |  |  |  | 7.3611 |  | First Floor Walls | 7 | Carpentry
2021-07-19 | Formwork for Ground floor level (100% complete) | 7.22 | GL7 | Modern Builders (Marlon) |  | 1 | 2846 |  | 2846 |  | Inv | L |  | 21071901 |  |  |  |  | GROUND FLOOR FORMWORK | 7 | Carpentry
2021-07-20 | Ready Mix (I extra meter of concrete) (7/9/2021) | 3.6 | FF12 | Ready Mix |  | 1 | 454.6 |  | 454.6 |  | Yes | M |  |  |  | Concrete | 3.6111 |  | First Floor Slab | 3 | Masonary
2021-07-20 | Scaffolding for 3 weeks (6 Flights) | 7.36 | FF13 | Williams Equiptment |  | 1 | 564 |  | 564 |  | Yes | U |  |  |  |  | 7.3611 |  | First Floor Plant | 7 | Carpentry
2021-07-25 | Light & Power | 8.04 | SL3 | BL&P |  | 1 | 15.9 |  | 15.9 |  | Yes | U |  |  |  |  | 8.0411 |  | First Floor Slab | 8 | Administrative
2021-07-26 | 2 Loads of 8" blocks | 7.36 | FF13 | Ready Block |  | 1 | 1823.6 |  | 1823.6 |  | Yes | M |  |  |  |  | 7.3611 |  | First Floor Walls | 7 | Carpentry
2021-07-26 | 300 4" blocks | 7.36 | FF13 | Ready Block |  | 1 | 619.23 |  | 619.23 |  | Yes | M |  |  |  |  | 7.3611 |  | First Floor Walls | 7 | Carpentry
2021-07-26 | Cement Mixer Rental | 3.1 | GL6 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | M |  |  |  |  | 3.1112 |  | First Floor Slab | 3 | Masonary
2021-07-27 | Land Tax | 8.01 | FF13 | Land Tax |  | 1 | 1664.55 |  | 1664.55 |  | Yes | M |  |  |  |  | 8.0111 |  | Administrative | 8 | Administrative
2021-07-27 | 1 Load of Cement | 3.16 | FF13 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  |  | 3.1611 |  | First Floor Walls | 3 | Masonary
2021-07-29 | Load of 8" Blocks | 3.46 | FF13 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 3.4611 |  | First Floor Walls | 3 | Masonary
2021-07-29 | Transfer to Local Rogers FCIB account | 8.01 | SL4 | Misc |  | 1 | 900 |  | 900 |  | Yes | M |  |  |  |  | 8.0111 |  | Administrative | 8 | Administrative
2021-08-06 | BWA Payment | 8.03 | SL3 | BWA |  | 1 | 35.2 |  | 35.2 |  | Yes | U |  |  |  |  | 8.0311 |  | Administrative | 8 | Administrative
2021-08-09 | Hilti Usage | 3.8 | FF13 | Ian Wiltshire |  | 1 | 400 |  | 400 |  | Yes | M |  | Ian080921 |  |  | 3.8117 |  | Plaster | 3 | Masonary
2021-08-09 | Diesel | 3.8 | FF13 | Ian Wiltshire |  | 1 | 50 |  | 50 | 20450 | Yes | M |  | Ian080921 |  |  | 3.8117 |  | Administrative | 3 | Masonary
2021-08-09 | 1 Load of Cement | 3.16 | FF13 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  | Cement | 3.1612 |  | Plaster | 3 | Masonary
2021-08-09 | Chq # 464 20k Plastering | 3.8 | SL4 | Ian Wiltshire |  | 1 | 10000 |  | 10000 |  | Yes | L |  | Ian080921 |  |  |  |  | First Floor Walls | 3 | Masonary
2021-08-09 | Chq # 464 20k Plastering | 3.8 | SL4 | Ian Wiltshire |  | 1 | 10000 |  | 10000 | 20000 | Yes | L |  | Ian080921 |  |  | 3.8117 |  | Plaster | 3 | Masonary
2021-08-10 | EXTENSION FROM CONT #8366184 Scaffolding for 3 weeks (6 Flights) | 7.36 | FF13 | Williams Equiptment |  | 1 | 105.75 |  | 105.75 |  | Yes | U |  |  |  |  | 7.3612 |  | First Floor Plant | 7 | Carpentry
2021-08-11 | Scaffold Extension | 7.36 | FF13 | Williams Equiptment |  | 1 | 246.75 |  | 246.75 |  | Yes | U |  |  |  |  | 7.3612 |  | First Floor Plant | 7 | Carpentry
2021-08-13 | Plumbing Supplies | 10.38 | FF13 | Carter & Company |  | 1 | 994.56 |  | 994.56 | 1241.31 | Yes | M |  | 3-00045209 |  |  | 10.3812 |  | Plumbing | 10 | Plumbing
2021-08-13 | Cement | 3.16 | FF13 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Inv | M |  |  |  |  | 3.1612 |  | Plaster | 3 | Masonary
2021-08-13 | Brian - Mixer 4 weeks 12-Jul to 11-Aug | 3.1 | GL6 | Brian Hinds |  | 1 | 1233.75 |  | 1233.75 |  | Yes | M |  | 3-00045209 |  |  | 7.3612 |  | Plaster | 3 | Masonary
2021-08-16 | August Bill | 8.04 | FF14 | BL&P |  | 1 | 16.5 |  | 16.5 |  | Yes | U |  |  |  |  | 8.0413 |  | Administrative | 8 | Administrative
2021-08-16 | 50lb box 3" common nails | 7.5 | FF14 | Marshall's Trading |  | 1 | 229.99 |  | 229.99 |  | Yes | M |  |  |  |  | 7.512 |  | Roof Construction | 7 | Carpentry
2021-08-18 | Formwork for first floor level (45% complete) | 7.4 | FF14 | Modern Builders (Marlon) |  | 1 | 4567.5 |  | 4567.5 |  | Yes | L |  | 21071901 |  |  | 7.4121 |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2021-08-18 | ARAWAK CEMENT GREY 42.5K | 3.16 | FF14 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  | 3-00045519 |  |  | 3.1612 |  | Roof Construction | 3 | Masonary
2021-08-19 | Toilet Rental ((Monthly Charge) | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  |  | 8.0413 |  | Ground Floor Plant | 8 | Administrative
2021-08-19 | Paid by Ian to Stephen Carter for props | 3.8 | FF13 | Ian Wiltshire |  | 1 | 375 |  | 375 |  | Yes | M |  |  |  |  | 3.814 |  | First Floor Walls | 3 | Masonary
2021-08-19 | Misc Plumbing | 10.38 | FF13 | Carter & Company |  | 1 | 1212.78 |  | 1212.78 |  | Inv | M |  | 3-00045624 |  |  |  |  | First Floor Walls | 10 | Plumbing
2021-08-19 | Misc Eletrical | 13.38 | FF13 | Carter & Company |  | 1 | 1212.78 |  | 1212.78 | 2425.56 | Yes | M |  | 3-00045624 |  |  | 13.3812 |  | First Floor Walls | 13 | Electrical
2021-08-19 | BRC Stirrups | 3.65 | FF14 | BRC West Indies |  | 1 | 1051.64 |  | 1051.64 |  | Yes | M |  |  |  |  | 3.6512 |  | Roof Construction | 3 | Masonary
2021-08-19 | Funds Transfervfor Construction | 1.11 | Xfer | Marcia (10K + Sievewright Rogers) |  | 1 | 70000 | -218.75 | 69781.25 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2021-08-21 | Misc Eletrical | 13.38 | FF14 | Emtage Electric |  | 1 | 572.84 | 100.25 | 673.09 |  | Yes | M |  |  |  |  | 13.3812 |  | Electrical Work | 13 | Electrical
2021-08-21 | Concrete Nails | 7.36 | FF14 | Carter & Company |  | 1 | 5.33 |  | 5.33 | 47.51 | Yes | M |  | 4218533 |  |  | 7.3612 |  | Roof Construction | 7 | Carpentry
2021-08-21 | Concrete Nails | 7.36 | FF14 | Carter & Company |  | 1 | 42.18 |  | 42.18 |  | Inv | M |  | 4218533 |  |  |  |  | Roof Construction | 7 | Carpentry
2021-08-23 | Two loads of Sand | 3.75 | FF13 | Shawn Grandison |  | 2 | 1300 |  | 2600 |  | Yes | M |  |  |  |  | 3.7513 |  | Site/Earthworks | 3 | Masonary
2021-08-24 | Initial 1/2 deposit on windows | 3.9 | FF15 | Meridian Windows |  | 1 | 3666.12 |  | 3666.12 | 10998.36 | Yes | M |  | WIN-7313 |  |  | 3.9127 |  | Windows | 3 | Masonary
2021-08-24 | Initial 1/2 deposit on windows | 3.9 | GL8 | Meridian Windows |  | 1 | 3666.12 |  | 3666.12 |  | Inv | M |  | WIN-7313 |  |  | 3.9126 |  | Windows | 3 | Masonary
2021-08-24 | Initial 1/2 deposit on windows | 3.9 | SL4 | Meridian Windows |  | 1 | 3666.12 |  | 3666.12 |  | Inv | M |  | WIN-7313 |  |  | 3.9126 |  | Windows | 3 | Masonary
2021-08-26 | External work plumbing (70% complete) | 10.38 | FF13 | Modern Builders (Marlon) |  | 1 | 1540 |  | 1540 |  | Inv | L |  | 21072601 |  |  |  |  | Plumbing | 10 | Plumbing
2021-08-26 | Formwork for first floor level (75% complete) | 7.4 | FF13 | Modern Builders (Marlon) |  | 1 | 3045 |  | 3045 |  | Inv | M |  | 21072601 |  |  |  |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2021-08-26 | Infrastructure to facilitate future HVAC installation in bedrooms (50%) | 4.1 | GL10 | Modern Builders (Marlon) |  | 1 | 1275 |  | 1275 | 5860 | Yes | L |  | 21072601 |  |  | 4.1128 |  | HVAC | 4 | HVAC
2021-08-28 | Diesel | 3.8 | FF13 | Ian Wiltshire |  | 1 | 50 |  | 50 |  | Yes | M |  |  |  |  | 3.814 |  | First Floor Walls | 3 | Masonary
2021-08-28 | 1 Load of Cement | 3.16 | FF15 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  | 3-00046344 |  |  | 3.1613 |  | First Floor Walls | 3 | Masonary
2021-08-30 | August Water Bill | 8.03 | SL3 | BWA |  | 1 | 79.57 |  | 79.57 |  | Yes | U |  |  |  |  | 8.0313 |  | Administrative | 8 | Administrative
2021-08-30 | 100 X 4" and 250 8" blocks | 3.46 | SL4 | Ready Block |  | 1 | 950.58 |  | 950.58 |  | Yes | M |  |  |  |  | 3.4613 |  | First Floor Walls | 3 | Masonary
2021-09-01 | Deposit for Sub Level French Door and Garage Windows production | 3.9 | SL4 | Odoll's Ltd |  | 1 | 2365 |  | 2365 |  | Yes | M |  |  |  |  | 3.9131 |  | Doors | 3 | Masonary
2021-09-10 | Deposit for 4 French Doors | 7.6 | FF15 | Kenrick Holder |  | 1 | 4042.5 |  | 4042.5 |  | Yes | M |  |  |  |  | 7.6132 |  | Doors | 7 | Carpentry
2021-09-15 | Container Renewal | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U |  |  |  |  | 5.4413 |  | SubFloor Plant | 5 | Earthworks
2021-09-15 | Mixer Rental | 3.1 | GL6 | Brian Hinds |  | 1 | 1233.75 |  | 1233.75 |  | Yes | M |  |  |  |  | 3.1132 |  | Plaster | 3 | Masonary
2021-09-16 | Formwork for first floor level (100% complete) | 7.4 | FF13 | Modern Builders (Marlon) |  | 1 | 2537.5 |  | 2537.5 |  | Yes | L |  |  |  |  | 7.4132 |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2021-09-21 | Ariana's Birthday | 8.04 | FF14 | Sievewright Rogers |  | 1 | 400 |  | 400 |  | Yes | M |  |  |  |  | 8.0414 |  | Administrative | 8 | Administrative
2021-09-22 | BL&P | 8.04 | FF14 | BL&P |  | 1 | 17.23 |  | 17.23 |  | Yes | U |  |  |  |  | 8.0413 |  | Administrative | 8 | Administrative
2021-09-22 | Scaffolding Extension | 7.36 | FF14 | Williams Equiptment |  | 1 | 1386.5 |  | 1386.5 |  | Yes | U |  |  |  |  | 7.3613 |  | Plaster | 7 | Carpentry
2021-09-22 | BWA Payment | 8.03 | SL3 | BWA |  | 1 | 79.57 |  | 79.57 |  | Yes | U |  |  |  |  | 8.0313 |  | Administrative | 8 | Administrative
2021-09-24 | Ring Beam Concrete | 3.06 | FF16 | Ready Mix |  | 1 | 7113.87 |  | 7113.87 |  | Yes | M |  |  |  | Concrete | 3.0614 |  | Roof Construction | 3 | Masonary
2021-09-29 | Initial 2/2 deposit on windows | 3.9 | FF15 | Meridian Windows |  | 1 | 3666.1233 |  | 3666.1233 |  | Inv | M |  | 763141 |  |  | 3.9135 |  | Windows | 3 | Masonary
2021-09-29 | Initial 2/2 deposit on windows | 3.9 | GL8 | Meridian Windows |  | 1 | 3666.1233 |  | 3666.1233 | 10998.37 | Yes | M |  | 763141 |  |  | 3.9137 |  | Windows | 3 | Masonary
2021-09-29 | Initial 2/2 deposit on windows | 3.9 | SL4 | Meridian Windows |  | 1 | 3666.1233 |  | 3666.1233 |  | Inv | M |  | 763141 |  |  | 3.9136 |  | Windows | 3 | Masonary
2021-10-02 | Masonary Services | 3.8 | GL7 | Ian Wiltshire |  | 1 | 20000 |  | 20000 |  | Yes | L |  |  |  |  | 3.8137 | Ian requesting 20k cheque to push through the remaining plastering, work to fill block holes, related terracing etc said now @$95k and that will put him @$115k. | SteelWork | 3 | Masonary
2021-10-05 | Cement | 7.36 | FF14 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  |  | 7.3614 |  | First Floor Walls | 7 | Carpentry
2021-10-06 | Concrete Vibrator Rental | 7.36 | FF14 | Williams Equiptment |  | 1 | 70.5 |  | 70.5 |  | Yes | U |  |  |  |  | 7.3614 |  | Roof Construction | 7 | Carpentry
2021-10-06 | Scaffold Extension to 15-Oct | 7.36 | FF14 | Williams Equiptment |  | 1 | 616.88 |  | 616.88 |  | Yes | U |  |  |  |  | 7.3614 |  | Roof Plant | 7 | Carpentry
2021-10-06 | Rebar (Steel) | 7.36 | FF14 | BRC West Indies |  | 1 | 3071.13 |  | 3071.13 |  | Yes | M |  |  |  |  | 7.3614 |  | Exterior Ground | 7 | Carpentry
2021-10-12 | Misc Masonary items | 7.36 | FF14 | Carter & Company |  | 1 | 185.3 |  | 185.3 | 740.05 | Yes | M |  | 3-00049902 |  |  | 7.3615 |  | Windows | 7 | Carpentry
2021-10-12 | 35 bags ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 35 | 14.85 | 35 | 554.75 |  | Inv | M |  | 3-00049902 |  |  |  |  | First Floor Walls | 7 | Carpentry
2021-10-12 | Transfer Funds to BIM | 1.11 | Xfer | Marcia (10K + Sievewright Rogers) |  | 1 | 80000 | -250 | 79750 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2021-10-13 | Load Of Sand | 3.75 | FF13 | Shawn Grandison |  | 1 | 1300 |  | 1300 |  | Inv | M |  | 1013202104 |  |  |  |  | Plaster | 3 | Masonary
2021-10-13 | Load Of Stone | 3.75 | FF13 | Shawn Grandison |  | 1 | 950 |  | 950 | 2250 | Yes | M |  | 1013202104 |  |  | 3.7514 |  | Plaster | 3 | Masonary
2021-10-13 | Concrete for Ring Beam upstand | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | 2073.87 |  | 2073.87 |  | Yes | M |  |  |  | Concrete | 3.0614 |  | Roof Construction | 3 | Masonary
2021-10-15 | Scaffold Extension to 29-Oct Rental contract # 8372524 | 7.36 | FF14 | Williams Equiptment |  | 1 | 246.75 |  | 246.75 | 575.75 | Yes | U |  | WILLRent10292021 |  |  | 7.3614 |  | First Floor Plant | 7 | Carpentry
2021-10-15 | Scaffold Extension to 29-Oct 8377562 | 7.36 | FF14 | Williams Equiptment |  | 1 | 329 |  | 329 |  | Inv | U |  | WILLRent10292021 |  |  |  |  | First Floor Plant | 7 | Carpentry
2021-10-19 | Toilet Rental ((Monthly Charge) (Sept to Nov) | 8.04 | EH0 | Infra Rentals |  | 1 | 611 |  | 611 |  | Yes | U |  |  |  |  | 8.0414 |  | Ground Floor Plant | 8 | Administrative
2021-10-19 | Exterior Pipe Scafolding Rental and Setup 10/21 - 11/22 (Additional 17 Flights $10 per day) | 7.36 | SL4 | SG Building Maintenance & Finishing Inc. |  | 23 | 170 | 160 | 4070 |  | Yes | U |  | 2021288 |  |  | 7.3614 |  | Roof Plant | 7 | Carpentry
2021-10-20 | Mixer Rental (10/4) | 3.1 | FF14 | Brian Hinds |  | 1 | 350 |  | 350 |  | Yes | M |  |  |  |  | 3.1147 |  | Plaster | 3 | Masonary
2021-10-20 | 35 bags ARAWAK CEMENT GREY 42.5K (Handling Charge) | 7.36 | FF14 | Carter & Company |  | 1 | 35 |  | 35 | 651.83 | Yes | M |  | 3-00050465 |  | Cement | 7.3615 |  | Plaster | 7 | Carpentry
2021-10-20 | 35 bags ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 35 | 14.85 | 97.08 | 616.83 |  | Inv | M |  | 3-00050465 |  | Cement |  |  | Plaster | 7 | Carpentry
2021-10-20 | Exterior Pipe Scafolding Rental and Setup 10/21 - 11/22 (Additional 7 Flights $10 per day) | 7.36 | SL4 | SG Building Maintenance & Finishing Inc. |  | 23 | 70 |  | 1610 |  | Yes | U |  | 2021-1288 |  |  | 7.3615 |  | Plaster | 7 | Carpentry
2021-10-21 | Erection of roof (15% complete) | 7.5 | FF16 | Modern Builders (Marlon) |  | 1 | 3754.5 |  | 3754.5 |  | Inv | L |  | 21102101 |  |  |  |  | Roof Construction | 7 | Carpentry
2021-10-21 | Placing electrical outlet and switch boxes | 13.38 | GL18 | Modern Builders (Marlon) |  | 1 | 2850 |  | 2850 | 6604.5 | Yes | L |  | 21102101 |  |  | 13.3815 |  | Electrical Work (Outlet and switch boxes rough-ins) | 13 | Electrical
2021-10-21 | BL&P (October) | 8.04 | SL3 | BL&P |  | 1 | 11.2 |  | 11.2 |  | Yes | U |  |  |  |  | 8.0415 |  | Administrative | 8 | Administrative
2021-10-22 | Misc Purchase ( nails etc) $84 refunded to Marlon for screws and nails purchased by carpenter. Bills total $90.36, difference was a personal pair of gloves. | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 90.36 | -6.36 | 84 |  | Yes | M |  |  |  |  | 7.3615 |  | Roof Construction | 7 | Carpentry
2021-10-22 | Nails | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 43.36 | -6.36 | 37 |  | Yes | L |  |  |  |  | 7.362 |  | Roof Construction | 7 | Carpentry
2021-10-22 | Additional wood for beams | 7.5 | FF16 | Carter & Company |  | 1 | 492.67 |  | 492.67 | 1118.64 | Yes | M |  | 3-00050758 |  |  | 7.515 |  | Roof Construction | 7 | Carpentry
2021-10-22 | Misc Masonary Items (nails screws, etc) | 3.75 | FF16 | Carter & Company |  | 1 | 459.36 | 166.61 | 625.97 |  | Inv | M |  | 3-00050758 |  |  |  |  | Plaster | 3 | Masonary
2021-10-26 | Container #1 Renewal (18-Oct to 17-Jan) | 5.44 | EH0 | Glassesco |  | 1 | 600 |  | 600 |  | Yes | U |  |  |  |  | 5.441 |  | SubFloor Plant | 5 | Earthworks
2021-10-27 | Water Supply | 8.03 | SL3 | BWA |  | 1 | 78.07 |  | 78.07 |  | Yes | U |  |  |  |  | 8.031 |  | Administrative | 8 | Administrative
2021-11-01 | Scaffold extension to 12-Nov. | 7.36 | FF14 | Williams Equiptment |  | 1 | 575.75 |  | 575.75 |  | Yes | U |  |  |  |  | 7.361 |  | Roof Plant | 7 | Carpentry
2021-11-02 | Scaffolding Extension 11/16 | 7.36 | FF14 | Williams Equiptment |  | 1 | 493.5 |  | 493.5 |  | Yes | U |  |  |  |  | 7.361 |  | Roof Plant | 7 | Carpentry
2021-11-02 | ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 1 | 651.83 |  | 651.83 |  | Yes | M |  |  |  |  | 3.1615 |  | Plaster | 7 | Carpentry
2021-11-03 | Misc Nails and Screws | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 50.06 |  | 50.06 |  | Yes | M |  |  |  |  | 7.3635 |  | Roof Construction | 7 | Carpentry
2021-11-04 | Erection of roof (45% complete) | 7.5 | FF16 | Modern Builders (Marlon) |  | 1 | 7509 |  | 7509 |  | Yes | L |  |  |  |  | 7.51 |  | Roof Construction | 7 | Carpentry
2021-11-10 | Hurricane Straps and nails | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 723.86 |  | 723.86 |  | Yes | M |  |  |  |  | 7.364 |  | Roof Construction | 7 | Carpentry
2021-11-10 | Mixer Rental | 3.1 | GL6 | Brian Hinds |  | 1 | 1233.75 |  | 1233.75 |  | Yes | U |  |  |  |  | 3.13 |  | Plaster | 3 | Masonary
2021-11-11 | Erection of roof (65% complete) | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 5006 |  | 5006 |  | Yes | L |  | 21111101 |  |  | 7.3625 |  | Roof Construction | 7 | Carpentry
2021-11-12 | Loads of Sand | 3.75 | FF13 | Shawn Grandison |  | 1 | 1300 |  | 1300 |  | Yes | M |  |  |  |  | 3.7515 |  | Plaster | 3 | Masonary
2021-11-12 | 1,208.92 Carter's stuff ad-mix + sheet hyrib Ian, 2×6 wood, pvc board...Marlon. Will send invoice when I see it. | 7.36 | FF14 | Modern Builders (Marlon) |  | 1 | 1208.92 |  | 1208.92 |  | Yes | M |  |  |  |  | 7.365 |  | Roof Construction | 7 | Carpentry
2021-11-13 | Scaffold extension | 7.36 | FF14 | Williams Equiptment |  | 1 | 359.12 |  | 359.12 |  | Yes | U |  |  |  |  | 7.361 |  | Roof Plant | 7 | Carpentry
2021-11-13 | 400 Hilty Use and 50 disel reimbursment | 3.8 | GL7 | Ian Wiltshire |  | 1 | 450 |  | 450 |  | Yes | U |  | Ian11132021 |  |  |  |  | Plaster | 3 | Masonary
2021-11-13 | Misc Masonary Services | 3.8 | GL7 | Ian Wiltshire |  | 1 | 20000 |  | 20000 | 20000 | Yes | L |  | Ian11132021 |  |  | 3.855 |  | Plaster | 3 | Masonary
2021-11-15 | Steel Crabs | 3.6 | FF14 | Structural Systems |  | 1 | 825.54 |  | 825.54 |  | Yes | M |  | 191409 |  |  | 3.645 |  | Plaster | 3 | Masonary
2021-11-15 | Concrete (rafter pour)) | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | 1603.88 |  | 1603.88 |  | Yes | M |  |  |  | Concrete | 3.0615 |  | Roof Construction | 3 | Masonary
2021-11-15 | Concrete Blocks Transportation | 3.8 | GL9 | Ready Block |  | 1 | 80 | 136.85 | 216.85 | 918.85 | Yes | M |  | RB-11152021 |  |  | 3.838 |  | Exterior Ground | 3 | Masonary
2021-11-16 | PVC Boards | 7.36 | FF15 | Carter & Company |  | 1 | 524.66 |  | 524.66 |  | Yes | M |  |  |  |  | 7.3616 |  | Roof Construction | 7 | Carpentry
2021-11-16 | Wood for Door Frames | 7.36 | FF15 | Carter & Company |  | 1 | 2787.15 |  | 2787.15 |  | Yes | M |  |  |  |  | 7.3617 |  | Doors | 7 | Carpentry
2021-11-17 | Toilet Renewal | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  |  | 8.041 |  | Ground Floor Plant | 8 | Administrative
2021-11-21 | Wood Primer & Paint (White) | 26.2 | FF19 | Harris Paint Barbados LTD |  | 1 | 723.22 |  | 723.22 |  | Yes | M |  |  |  |  | 26.21 |  | Painting (Finishes & Trim) | 26 | Painting
2021-11-23 | Permaclad Sheeting and parts | 7.5 | FF14 | BRC West Indies |  | 1 | 12626.96 | 2209.72 | 14836.68 |  | Yes | M |  |  |  |  | 7.51 |  | Roof Construction | 7 | Carpentry
2021-11-23 | Electric Bill November | 8.04 | FF14 | BL&P |  | 1 | 20.06 |  | 20.06 |  | Yes | U |  |  |  |  | 8.042 |  | Administrative | 8 | Administrative
2021-11-23 | Pipe scaffold to 22-Dec. | 7.36 | SL4 | SG Building Maintenance & Finishing Inc. |  | 1 | 5280 |  | 5280 |  | Yes | U |  |  |  |  | 7.3615 |  | First Floor Plant | 7 | Carpentry
2021-11-25 | Credit Refund) Concrete (rafter pour)) | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | -160.39 |  | -160.39 |  | Yes | M |  |  |  | Concrete | 3.061 |  | Roof Construction | 3 | Masonary
2021-11-26 | Trowel Plastic (665 lbs Apple and 665 lbs Elegance) | 26.2 | SL17 | Trowel Plastic |  | 1 | 4210.37 | 736.82 | 4947.19 |  | Yes | M |  | QT00009299 |  |  | 26.21 |  | Painting (Finishes & Trim) | 26 | Painting
2021-11-27 | Screws (Screws $79.11 Exchange of screws previous delivered. Payment of difference plus purchase of another box.) | 7.36 | FF15 | Carter & Company |  | 1 | 79.11 |  | 79.11 |  | Yes | M |  |  |  |  | 7.361 |  | Roof Construction | 7 | Carpentry
2021-11-27 | Cement | 3.16 | FF15 | Carter & Company |  | 35 | 14.85 |  | 519.75 |  | Inv | M |  | 3-00053726 |  |  |  |  | Plaster | 3 | Masonary
2021-11-27 | Other Masonary Misc | 3.16 | FF15 | Carter & Company |  | 1 | 382.16 | 280.99 | 663.15 | 1886.65 | Yes | M |  | 3-00053726 |  |  | 3.162 |  | Plaster | 3 | Masonary
2021-11-27 | Treated Pine | 7.36 | GL18 | Carter & Company |  | 25 | 28.15 |  | 703.75 |  | Inv | M |  | 3-00053726 |  |  |  |  | Roof Construction | 7 | Carpentry
2021-11-29 | Windows Caulk | 3.7 | FF15 | Meridian Windows |  | 1 | 2538 |  | 2538 |  | Yes | M |  |  |  |  | 3.715 |  | Windows | 3 | Masonary
2021-11-29 | xfer from (Marcia) | 1.11 | Xfer | Marcia Rogers |  | 1 | 20000 | -62.5 | 19937.5 |  | Yes | X |  |  |  |  | 3.162 |  | Administrative | 1 | Transfers
2021-12-01 | Concrete Blocks 8" | 3.8 | GL9 | Ready Block |  | 225 | 2.32 |  | 522 |  | Inv | M |  | RB-11152021 |  |  |  |  | Exterior Ground | 3 | Masonary
2021-12-01 | Concrete Blocks 6" | 3.8 | GL9 | Ready Block |  | 100 | 1.8 |  | 180 |  | Inv | M |  | RB-11152021 |  |  |  |  | Exterior Ground | 3 | Masonary
2021-12-04 | Misc Masonary Items | 3.8 | FF15 | Carter & Company |  | 1 | 264.93 |  | 264.93 |  | Yes | M |  | 30402399.48 |  |  | 3.81 |  | Windows | 3 | Masonary
2021-12-07 | BL&P | 8.04 | SL3 | BL&P |  | 1 | 18.18 |  | 18.18 |  | Yes | U |  |  |  |  | 8.0425 |  | Administrative | 8 | Administrative
2021-12-09 | Reimbursment for Roofing Screws | 7.36 | FF15 | Hothersal Trading |  | 1 | 92.33 |  | 92.33 |  | Inv | M |  | misc120921_ModBUild |  |  |  |  | Roof Construction | 7 | Carpentry
2021-12-09 | Reimbursment for Roofing Screws | 7.36 | FF15 | Marshall's Trading |  | 1 | 44.65 |  | 44.65 |  | Inv | M |  | misc120921_ModBUild |  |  |  |  | Roof Construction | 7 | Carpentry
2021-12-09 | Reimbursment for Roofing Screws | 7.36 | FF15 | BRC West Indies |  | 1 | 470 |  | 470 |  | Inv | M |  | misc120921_ModBUild |  |  |  |  | Roof Construction | 7 | Carpentry
2021-12-09 | Reimbursment for Sqr Deck Screws | 7.36 | FF15 | Fasteners Barbados LTD |  | 1 | 84.6 |  | 84.6 | 691.58 | Yes | M |  | misc120921_ModBUild |  |  | 7.3625 |  | Roof Construction | 7 | Carpentry
2021-12-09 | Roof 89% complete | 7.36 | FF15 | Modern Builders (Marlon) |  | 1 | 3754.5 |  | 3754.5 |  | Inv | L |  | 21120901 |  |  |  |  | Roof Construction | 7 | Carpentry
2021-12-09 | Door Frames | 7.36 | FF15 | Modern Builders (Marlon) |  | 1 | 1150 |  | 1150 |  | Inv | L |  | 21120901 |  |  |  |  | Doors | 7 | Carpentry
2021-12-09 | Laborers for casting ring beam rafter fill | 7.36 | FF15 | Modern Builders (Marlon) |  | 1 | 450 |  | 450 | 5354.5 | Yes | L |  | 21120901 |  |  | 7.362 |  | Roof Construction | 7 | Carpentry
2021-12-10 | xfer from | 1.11 | Xfer | Sievewright Rogers |  | 1 | 40000 | -125 | 39875 |  | Yes | X |  |  |  |  | 7.3625 |  | Administrative | 1 | Transfers
2021-12-12 | Xfer to M & S account for insurance & misc purchases | 8.01 | FF15 | Xfer |  | 1 | 2000 |  | 2000 |  | Yes | M | [6 empty] | Administrative | 8 | Administrative
2021-12-13 | ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 1 | 695.01 |  | 695.01 |  | Yes | M |  |  |  |  | 7.3635 |  | Plaster | 7 | Carpentry
2021-12-13 | Permaclad flashing | 7.36 | FF15 | BRC West Indies |  | 1 | 144.64 |  | 144.64 |  | Yes | M |  |  |  |  | 7.363 |  | Roof Construction | 7 | Carpentry
2021-12-14 | Purchase of Mortar Mix and Misc. concrete nails | 3.8 | FF15 | Marcia Rogers |  | 1 | 130.07 |  | 130.07 |  | Yes | M |  |  |  |  | 3.81 |  | Windows | 3 | Masonary
2021-12-14 | Reimbursement for Purchase of Mortar Mix and Misc. concrete nails | 1.11 | FF15 | Marcia Rogers |  | 1 | 130.07 |  | 130.07 |  | Yes | X |  |  |  |  | 3.815 |  | Administrative | 1 | Transfers
2021-12-16 | extension of scaffold as per email sent | 7.36 | FF14 | Williams Equiptment |  | 1 | 2138.5 |  | 2138.5 |  | Yes | U |  |  |  |  | 7.3615 |  | Roof Plant | 7 | Carpentry
2021-12-16 | 3 weeks use of the mixer between 11-Nov and 10-Dec. | 3.1 | GL6 | Brian Hinds |  | 1 | 1050 |  | 1050 |  | Yes | U |  |  |  |  | 3.11 |  | Plaster | 3 | Masonary
2021-12-20 | Guttering parts | 26.5 | FF14 | Wolseley |  | 1 | 2536.83 | 10 | 2546.83 |  | Yes | M |  |  |  |  | 10.41 |  | Roof Construction | 26 | Painting
2021-12-21 | Facia Board painting | 26.4 | FF19 | Desmond (Harclyde Bedford) |  | 1 | 1600 |  | 1600 |  | Inv | L |  | Des12212021 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2021-12-21 | Misc Painting Supplies Refund | 26.4 | FF19 | Desmond (Harclyde Bedford) |  | 1 | 38.93 |  | 38.93 | 1638.93 | Yes | M |  | Des12212021 |  |  | 26.415 |  | Painting (Finishes & Trim) | 26 | Painting
2021-12-24 | Masonary Services | 3.8 | FF13 | Ian Wiltshire |  | 1 | 1000 |  | 1000 |  | Yes | L |  | Ian01292022 |  |  | 3.81 |  | Water Tank | 3 | Masonary
2021-12-24 | Masonary Services | 3.8 | FF13 | Ian Wiltshire |  | 1 | 9000 |  | 9000 | 10000 | Yes | L |  | Ian01292022 |  |  | 3.81 |  | Windows | 3 | Masonary
2021-12-28 | $510. Container #2 Expired 6-Dec. Extended 2 months to 6-Feb. | 5.44 | EH0 | 5.44 | EH0 | 1 | 510 |  | 510 |  | Yes | U |  |  |  |  | 5.4415 |  | SubFloor Plant | 5 | Earthworks
2021-12-28 | Toilet Renewal | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  |  | 8.0415 |  | First Floor Plant | 8 | Administrative
2021-12-28 | Water Supply Nov thru Dec | 8.03 | SL3 | BWA |  | 1 | 168.38 |  | 168.38 |  | Yes | U |  |  |  |  | 8.031 |  | Administrative | 8 | Administrative
2021-12-30 | 10 bags of fiber Mesh for Concrete | 3.8 | FF15 | Greg (From Carters) |  | 10 | 14.7 | 25.73 | 172.73 |  | Yes | M | Greg |  | SR In Store |  | 3.81 |  | Windows | 3 | Masonary
2022-01-03 | Scaffolding Extension | 7.36 | SL17 | Williams Equiptment |  | 1 | 1069.25 |  | 1069.25 |  | Yes | U |  |  |  |  | 7.3615 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-01-05 | Mortor Bond PVA | 3.8 | FF15 | Greg (From Carters) |  | 1 | 67.57 |  | 67.57 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 3.81 |  | Windows | 3 | Masonary
2022-01-05 | Misc Concrete Nails | 3.8 | FF15 | Greg (From Carters) |  | 1 | 31.47 |  | 31.47 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 3.815 |  | Windows | 3 | Masonary
2022-01-06 | Stainless Steel Butt/hinges | 7.8 | GL18 | Greg (From Carters) |  | 1 | 231.45 |  | 231.45 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 7.81 |  | Doors | 7 | Carpentry
2022-01-07 | 8 Parliament Hinges Brass | 7.8 | GL18 | Greg (From Blades & Williams) |  | 1 | 134.51 |  | 134.51 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 7.815 |  | Doors | 7 | Carpentry
2022-01-08 | Door Bolts and Deabolt Locks | 7.8 | GL18 | Greg (From Carters) |  | 1 | 600.1 |  | 600.1 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 7.81 |  | Doors | 7 | Carpentry
2022-01-12 | ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 1 | 695.01 |  | 695.01 |  | Yes | M |  |  |  |  | 7.3615 |  | Exterior Ground | 7 | Carpentry
2022-01-12 | Final Deposit on Exterior Doors | 7.6 | FF15 | Kenrick Holder |  | 1 | 4042.5 |  | 4042.5 |  | Yes | M |  |  |  |  | 7.61 |  | Doors | 7 | Carpentry
2022-01-12 | Wood Filler & Silicone | 26.3 | GL18 | Marshall's Trading |  | 1 | 151.58 |  | 151.58 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 26.31 |  | Painting (Finishes & Trim) | 26 | Painting
2022-01-12 | Tying Wire for steel mats and cages | 3.8 | GL9 | BRC West Indies |  | 1 | 51.7 |  | 51.7 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 3.815 |  | Exterior Ground | 3 | Masonary
2022-01-13 | Therminex Pesticide Treatment 1Gal | 5.67 | GL11 | Discount Hardware Store, Charles Rowe Bridge |  | 1 | 237.75 |  | 237.75 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 5.671 |  | Site/Earthworks | 5 | Earthworks
2022-01-14 | Dig stairway, fence and pathway footing and brush removal | 5.67 | GL11 | Shawn Grandison |  | 1 | 935 |  | 935 |  | Yes | L |  |  |  |  | 5.671 |  | Site/Earthworks | 5 | Earthworks
2022-01-14 | Barbados Light & Power | 8.04 | GL11 | BL&P |  | 1 | 21.31 |  | 21.31 |  | Yes | U |  |  |  |  | 8.043 |  | Administrative | 8 | Administrative
2022-01-14 | Cement Mixer (12/11/2021 to 1/10/2022 | 3.1 | GL11 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | U |  |  |  |  | 3.135 |  | Exterior Ground | 3 | Masonary
2022-01-14 | Load of 8" Blocks | 3.8 | GL9 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 3.825 |  | Exterior Ground | 3 | Masonary
2022-01-14 | Scaffolding Extension till 1/28 | 7.36 | SL17 | Williams Equiptment |  | 1 | 1069.25 |  | 1069.25 |  | Yes | U |  |  |  |  | 7.362 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-01-15 | 30 % Exterior Trowel Plastering | 26.5 | SL17 | Desmond (Harclyde Bedford) |  | 1 | 3000 |  | 3000 |  | Inv | L |  | Des01152022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-01-15 | Misc Purchases (masking tape etc) | 26.5 | SL17 | Desmond (Harclyde Bedford) |  | 1 | 81.59 |  | 81.59 | 3081.59 | Yes | M |  | Des01152022 |  |  | 26.545 |  | Painting (Finishes & Trim) | 26 | Painting
2022-01-17 | 3 X Teledo dbl comboset S/S locks | 7.8 | GL18 | Carter & Company |  | 3 | 35.19 | 18.47 | 124.04 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 7.81 |  | Doors | 7 | Carpentry
2022-01-20 | Commanding T strips for French doors | 7.6 | FF15 | Kenrick Holder |  | 4 | 75 |  | 300 |  | Yes | M |  |  |  |  | 7.625 |  | Doors | 7 | Carpentry
2022-01-20 | 8 meters of Sand | 5.67 | GL11 | Shawn Grandison |  | 1 | 1145 |  | 1145 |  | Yes | M |  |  |  |  | 5.671 |  | Exterior Ground | 5 | Earthworks
2022-01-20 | Skip to collect rubbish | 5.67 | GL11 | Garbage Gobbler |  | 1 | 146.9 |  | 146.9 |  | Yes | U |  |  |  |  | 5.6715 |  | Exterior Ground | 5 | Earthworks
2022-01-20 | Container #1 extended 2 months from 18-Jan. $510.00 | 5.67 | GL11 | Glassesco |  | 1 | 510 |  | 510 |  | Yes | U |  |  |  |  | 5.672 |  | Exterior Ground | 5 | Earthworks
2022-01-20 | 8 meters of sand | 5.67 | SL2 | Shawn Grandison |  | 1 | 1145 |  | 1145 |  | Inv | M |  | SG02172020 |  |  |  |  | Exterior Ground | 5 | Earthworks
2022-01-25 | Small skip 2 cubic metres ordered for delivery tomorrow. $124.55 for one day | 5.67 | GL11 | RM Garbage Master LTD |  | 1 | 124.55 |  | 124.55 |  | Yes | U |  |  |  |  | 5.671 |  | Exterior Ground | 5 | Earthworks
2022-01-25 | Hilti Nails & Shots | 7.9 | GL18 | Williams Equiptment |  | 1 | 376 |  | 376 |  | Yes | M | Out of Pocket (Greg) | 207261962 | SR In Store |  | 7.91 |  | Ceiling | 7 | Carpentry
2022-01-25 | Ceiling material for Ground & 1st FL | 7.9 | GL18 | Carter & Company |  | 1 | 9173.59 |  | 9173.59 |  | Yes | M |  |  |  |  | 7.915 |  | Ceiling | 7 | Carpentry
2022-01-27 | Off Hours Site Cleanup | 3.8 | FF13 | Nicholas Small |  | 1 | 175 |  | 175 |  | Yes | U |  |  |  |  | 3.81 |  | Exterior Ground | 3 | Masonary
2022-01-27 | Mortor Bond PVA | 3.8 | GL18 | Greg (From Carters) |  | 2 | 57.506 | 20.13 | 135.142 |  | Yes | M | Out of Pocket (Greg) |  | SR In Store |  | 3.81 |  | Plaster | 3 | Masonary
2022-01-28 | Building window cills (20 no. @ $55/each) | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | 1100 |  | 1100 |  | Inv | L |  | 22012701 |  |  |  |  | Windows | 7 | Carpentry
2022-01-28 | Building & Installing door frames (75 % complete) | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | 3450 |  | 3450 |  | Inv | L |  | 22012701 |  |  |  |  | Doors | 7 | Carpentry
2022-01-28 | Less previous payment received for building & installing door frames | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | -1150 |  | -1150 |  | Inv | L |  | 22012701 |  |  |  |  | Doors | 7 | Carpentry
2022-01-28 | Installing external doors (5 no. @ $80/ each) | 7.8 | FF15 | Modern Builders (Marlon) |  | 5 | 80 |  | 400 |  | Inv | L |  | 22012701 |  |  |  |  | Doors | 7 | Carpentry
2022-01-28 | Installation of door locks (4 no. @ $55 /each) | 7.8 | FF15 | Modern Builders (Marlon) |  | 4 | 55 |  | 220 |  | Inv | L |  | 22012701 |  |  |  |  | Doors | 7 | Carpentry
2022-01-28 | Installation of bolts (4 no. @ $20 /each) | 7.8 | FF15 | Modern Builders (Marlon) |  | 4 | 20 |  | 80 |  | Inv | L |  | 22012701 |  |  |  |  | Doors | 7 | Carpentry
2022-01-28 | Building and installing decorative cap formwork (37ft @ $22/ft) | 7.8 | GL18 | Modern Builders (Marlon) |  | 1 | 814 |  | 814 | 4914 | Yes | L |  | 22012701 |  |  | 7.845 |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2022-01-28 | Transfer to Local Rogers FCIB account | 8.01 | SL4 | Misc |  | 1 | 1500 |  | 1500 |  | Yes | M |  |  |  |  | 8.015 |  | Administrative | 8 | Administrative
2022-01-28 | Transfer Funds to BIM | 1.11 | Xfer | Sievewright Rogers |  | 1 | 50000 | -156.25 | 49843.75 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2022-01-29 | Masonary Services | 3.8 | FF16 | Ian Wiltshire |  | 1 | 5000 |  | 2000 |  | Inv | L |  | Ian01292022 |  |  |  |  | Foundation Extras Work | 3 | Masonary
2022-01-29 | Masonary Services | 3.8 | FF16 | Ian Wiltshire |  | 1 | 5000 |  | 3000 |  | Inv | L |  | Ian01292022 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-01-29 | Masonary Services | 3.8 | FF16 | Ian Wiltshire |  | 1 | 5000 |  | 400 | 20000 | Inv | L |  | Ian01292022 |  |  |  |  | Water Tank | 3 | Masonary
2022-01-29 | Diesel | 3.8 | FF19 | Ian Wiltshire |  | 1 | 50 |  | 50 |  | Inv | U |  | Ian01292022 |  |  |  |  | Site/Earthworks | 3 | Masonary
2022-01-29 | Masonary Services | 3.8 | GL18 | Ian Wiltshire |  | 1 | 5000 |  | 5000 |  | Yes | L |  | Ian01292022 |  |  | 3.83 |  | Foundation Extras Work | 3 | Masonary
2022-01-29 | Masonary Services | 3.8 | GL18 | Ian Wiltshire |  | 1 | 5000 |  | 5000 |  | Inv | L |  | Ian01292022 |  |  |  |  | SteelWork | 3 | Masonary
2022-01-29 | Masonary Services | 3.8 | SL17 | Ian Wiltshire |  | 1 | 5000 |  | 5000 |  | Inv | L |  | Ian01292022 |  |  |  |  | Plaster | 3 | Masonary
2022-01-31 | Electrical Supplies | 13.3 | FF13 | Carter & Company |  | 1 | 5817.73 |  | 5817.73 |  | Yes | M |  |  |  |  | 13.31 |  | Electrical Work | 13 | Electrical
2022-02-05 | Weldcrete and screws for the apartment windows. | 3.8 | SL5 | Carter & Company |  | 1 | 417.45 |  | 417.45 |  | Yes | M |  |  |  |  | 3.81 |  | Windows | 3 | Masonary
2022-02-08 | ARAWAK CEMENT GREY 42.5K | 7.36 | FF14 | Carter & Company |  | 1 | 695.01 |  | 695.01 |  | Yes | M |  |  |  |  | 7.3615 |  | Exterior Ground | 7 | Carpentry
2022-02-11 | Scaffold extension 29-Jan to 18-Feb | 7.9 | GL18 | Williams Equiptment |  | 1 | 1603.88 |  | 1603.88 |  | Yes | U |  |  |  |  | 7.91 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-02-12 | Marking Paint | 3.8 | SL5 | Carter & Company |  | 1 | 15 |  | 15 |  | Yes | M |  |  |  |  | 3.81 |  | Exterior Ground | 3 | Masonary
2022-02-14 | Ceiling material for Ground & 1st FL (Gypson Board) | 7.9 | GL18 | Carter & Company |  | 1 | 2886.04 | 505.0576 | 3391.0976 |  | Inv | M |  | Cat3-00059380 |  |  |  |  | Ceiling | 7 | Carpentry
2022-02-14 | Drywall Screws | 7.9 | GL18 | Carter & Company |  | 1 | 291.78 | 51.0616 | 342.8416 |  | Inv | M |  | Cat3-00059380 |  |  |  |  | Ceiling | 7 | Carpentry
2022-02-14 | Plumbing Supplies | 10.38 | GL18 | Carter & Company |  | 1 | 627.89 | 109.8809 | 737.7709 | 4471.71 | Yes | M |  | Cat3-00059380 |  |  | 10.383 |  | Fixtures & Fittings | 10 | Plumbing
2022-02-14 | Jan-22 Water Bill | 8.03 | SL3 | BWA |  | 1 | 84.9 |  | 84.9 |  | Yes | M |  |  |  |  | 8.0335 |  | Administrative | 8 | Administrative
2022-02-14 | Water Supply | 8.03 | SL3 | BWA |  | 1 | 76.37 |  | 76.37 |  | Yes | U |  |  |  |  | 8.0315 |  | Administrative | 8 | Administrative
2022-02-14 | Grease Traps | 3.8 | SL5 | Ian Wiltshire |  | 2 | 375 |  | 750 |  | Yes | M |  |  |  |  | 3.815 |  | Exterior Ground | 3 | Masonary
2022-02-15 | Toilet Rental | 8.04 | EH0 | Infra Rentals |  | 1 | 611.5 |  | 611.5 |  | Yes | U |  |  |  |  | 8.0425 |  | Exterior Ground | 8 | Administrative
2022-02-15 | Erection of suspended ceilings (60 %) | 7.9 | FF19 | Modern Builders (Marlon) |  | 1 | 4317 |  | 4317 |  | Inv | L |  | MB-22021501 |  |  |  |  | Ceiling | 7 | Carpentry
2022-02-15 | 50% payment for the laminated beams and columns to Joiner (Roger Forde) | 7.51 | GL11 | Modern Builders (Marlon) | 3530 | 1 | 1765 |  | 1765 |  | Inv | M |  | RF-02152022 |  |  | 7.512 | Joiner doesn't do online banking so have to pay him through Modern Builders | Laminated Beams for Patio | 7 | Carpentry
2022-02-15 | 50% payment for the laminated beams and columns to Joiner (Roger Forde) | 7.51 | GL11 | Modern Builders (Marlon) | 3530 | 1 | 1765 |  | 1765 | 3530 | Yes | L |  | RF-02152022 |  |  | 7.5115 | Joiner doesn't do online banking so have to pay him through Modern Builders | Laminated Beams for Patio | 7 | Carpentry
2022-02-15 | Electric Supply | 8.04 | GL11 | BL&P |  | 1 | 16.11 |  | 16.11 |  | Yes | U |  |  |  |  | 8.041 |  | Administrative | 8 | Administrative
2022-02-15 | Concrete Mixer usage of 2 weeks and 3 days between 11-Jan and 10-Feb | 3.1 | GL11 | Brian Hinds |  | 1 | 910 |  | 910 |  | Yes | U |  |  |  |  | 3.115 |  | Exterior Ground | 3 | Masonary
2022-02-15 | Erection of suspended ceilings (60 %) | 7.9 | GL18 | Modern Builders (Marlon) |  | 1 | 4317 |  | 4317 | 8634 | Yes | L |  | MB-22021501 |  |  | 7.915 |  | Ceiling | 7 | Carpentry
2022-02-17 | 5 hrs of excavator work @150 per hr | 5.42 | SL2 | Shawn Grandison |  | 5 | 150 |  | 750 | 1895 | Yes | L |  | SG02172020 |  |  | 5.4215 |  | Exterior Ground | 5 | Earthworks
2022-02-18 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 50000 | -156.25 | 49843.75 |  | Yes | X |  |  |  |  | 3.115 |  | Administrative | 1 | Transfers
2022-02-21 | Water resistant SHEETROCK 1-2 4X8 P-REY MOLD | 7.9 | GL18 | Marshall's Trading |  | 11 | 36.95 | 71.13 | 477.58 |  | Yes | M |  |  |  |  | 7.91 |  | Ceiling | 7 | Carpentry
2022-02-22 | Cement & Mortar | 3.8 | GL10 | Carter & Company |  | 1 | 844.66 |  | 844.66 |  | Yes | M |  |  |  |  | 3.825 |  | Exterior Ground | 3 | Masonary
2022-02-22 | Initial Water connection fee balance | 8.03 | SL3 | BWA |  | 1 | 78.68 |  | 78.68 |  | Yes | U |  |  |  |  | 8.031 |  | Administrative | 8 | Administrative
2022-02-25 | Scaffold extension to 25-Feb | 7.9 | GL18 | Williams Equiptment |  | 1 | 534.62 |  | 534.62 |  | Yes | U |  |  |  |  | 7.91 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-02-26 | Fiber Mesh 2 lb for cement | 3.8 | GL10 | Carter & Company |  | 1 | 92.7 |  | 92.7 |  | Inv | M |  | 3-00060307 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-02-26 | Painting Supplies | 26.5 | GL18 | Carter & Company |  | 1 | 1042.99 | 198.75 | 1241.74 | 1334.44 | Yes | M |  | 3-00060307 |  |  | 26.52 |  | Painting (Finishes & Trim) | 26 | Painting
2022-02-28 | Two Interior dors | 7.9 | GL9 | Carter & Company |  | 1 | 632.62 |  | 632.62 |  | Yes | M |  |  |  |  | 7.91 |  | Doors | 7 | Carpentry
2022-03-01 | 5 Meters of Stone | 5.67 | SL2 | Shawn Grandison |  | 1 | 650 |  | 650 |  | Yes | M |  |  |  |  | 5.672 |  | Exterior Ground | 5 | Earthworks
2022-03-03 | SikaFlex | 3.7 | FF15 | Meridian Windows |  | 1 | 1080.02 |  | 1080.02 |  | Yes | M |  |  |  |  | 3.735 |  | Windows | 3 | Masonary
2022-03-03 | Erections of Ceilings | 7.9 | FF19 | Modern Builders (Marlon) |  | 1 | 5756 |  | 5756 |  | Inv | L |  | 22030301 |  |  |  |  | Ceiling | 7 | Carpentry
2022-03-03 | Final 50% payment for the laminated beams and columns to Joiner (Roger Forde) | 7.51 | GL11 | Modern Builders (Marlon) |  | 1 | 1765 |  | 1765 |  | Yes | M |  |  |  |  | 7.511 |  | Laminated Beams for Patio | 7 | Carpentry
2022-03-03 | Final 50% payment for the laminated beams and columns to Joiner (Roger Forde) | 7.51 | GL11 | Modern Builders (Marlon) |  | 1 | 1765 |  | 1765 |  | Yes | L |  |  |  |  | 7.5115 |  | Laminated Beams for Patio | 7 | Carpentry
2022-03-03 | Plumbing Supplies | 10.38 | GL18 | Carter & Company |  | 1 | 655.22 |  | 655.22 |  | Yes | M |  |  |  |  | 10.384 |  | Fixtures & Fittings | 10 | Plumbing
2022-03-03 | Placing electrical outlet and switch boxes | 13.38 | GL18 | Modern Builders (Marlon) |  | 1 | 2860 |  | 2860 | 8616 | Yes | L |  | 22030301 |  |  | 13.3825 |  | Electrical Work (Outlet and switch boxes rough-ins) | 13 | Electrical
2022-03-03 | Misc Electrical items (Reim to Marlon) | 13.38 | GL18 | Modern Builders (Marlon) |  | 1 | 1192.05 |  | 1192.05 |  | Yes | M |  |  |  |  | 13.383 |  | Electrical Work | 13 | Electrical
2022-03-07 | Shower Mixers BIM Shipping Cost | 10.38 | GL18 | Laparkan |  | 1 | 228.66 |  | 228.66 |  | Yes | M |  |  |  |  | 10.381 |  | Fixtures & Fittings | 10 | Plumbing
2022-03-08 | First FL Lily White Ceiling Trowel Plastic (665 lbs) | 26.2 | FF19 | Trowel Plastic |  | 1 | 3216.48 | 562.88 | 3779.36 |  | Yes | M |  |  |  |  | 26.215 |  | Painting (Finishes & Trim) | 26 | Painting
2022-03-09 | Masonary Supplies | 3.06 | FF16 | Carter & Company |  | 1 | 234.92 | 41.111 | 276.031 |  | Inv | M |  | Ian030922 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-03-09 | ARAWAK CEMENT GREY 42.5K | 3.06 | FF16 | Carter & Company |  | 20 | 15.9 | 55.65 | 373.65 |  | Inv | M |  | Ian030922 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-03-09 | Cement Handling Charges | 3.06 | FF16 | Carter & Company |  | 20 | 1 | 3.5 | 23.5 | 673.18 | Yes | M |  | Ian030922 |  |  | 3.0625 |  | Exterior Ground | 3 | Masonary
2022-03-10 | Load of 8" Blocks | 3.8 | GL10 | Ready Block |  | 1 | 911.8 |  | 911.8 |  | Yes | M |  |  |  |  | 3.81 |  | Ground Floor Walls | 3 | Masonary
2022-03-15 | Barbados Light & Power | 8.04 | GL11 | BL&P |  | 1 | 19.8 |  | 19.8 |  | Yes | M |  |  |  |  | 8.041 |  | Administrative | 8 | Administrative
2022-03-16 | Container Rental | 5.67 | GL11 | Glassesco |  | 1 | 255 |  | 255 |  | Yes | M |  |  |  |  | 5.6715 |  | Exterior Ground | 5 | Earthworks
2022-03-17 | Toilet rental | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | M |  |  |  |  | 8.0425 |  | Exterior Ground | 8 | Administrative
2022-03-18 | Misc Plumbing Supplies | 10.38 | FF13 | Modern Builders (Marlon) |  | 1 | 127.18 |  | 127.18 |  | Inv | M |  | MB-03182022 | [5 empty] | 10 | Plumbing
2022-03-18 | ARAWAK CEMENT GREY 42.5K | 7.8 | FF19 | Carter & Company |  | 1 | 397.15 |  | 397.15 |  | Yes | M |  |  |  |  | 7.89 |  | Exterior Ground | 7 | Carpentry
2022-03-18 | Misc Carpentry Supplies | 7.8 | FF19 | Modern Builders (Marlon) |  | 1 | 691.3 |  | 691.3 |  | Inv | M |  | MB-03182022 | [5 empty] | 7 | Carpentry
2022-03-18 | Misc Carpentry Supplies | 7.8 | FF19 | Modern Builders (Marlon) |  | 1 | 22.67 |  | 22.67 |  | Inv | M |  | MB-03182022 | [5 empty] | 7 | Carpentry
2022-03-18 | Misc Carpentry Supplies | 7.8 | FF19 | Modern Builders (Marlon) |  | 1 | 376 |  | 376 |  | Inv | M |  | MB-03182022 | [5 empty] | 7 | Carpentry
2022-03-18 | Misc Carpentry Supplies | 7.8 | FF19 | Modern Builders (Marlon) |  | 1 | 159.81 |  | 159.81 |  | Inv | M |  | MB-03182022 | [5 empty] | 7 | Carpentry
2022-03-18 | Misc Carpentry Supplies | 7.8 | FF19 | Modern Builders (Marlon) |  | 1 | 89.9 |  | 89.9 | 1466.86 | Yes | M |  | MB-03182022 |  |  | 7.812 |  |  | 7 | Carpentry
2022-03-19 | Hilti Use on footing (Greg Yearwood (Ian)) | 5.44 | EH0 | Ian Wiltshire |  | 1 | 640 |  | 640 |  | Yes | U |  |  |  |  | 5.4425 |  | Subfloor Slab | 5 | Earthworks
2022-03-20 | Windows for garage | 3.7 | FF15 | Meridian Windows |  | 1 | 999.43 |  | 999.43 |  | Yes | M |  |  |  |  | 3.73 |  | Windows | 3 | Masonary
2022-03-22 | Cement Mixer Rental (Feb _ March) | 3.1 | GL11 | Brian Hinds |  | 1 | 1190 |  | 1190 |  | Yes | M |  |  |  |  | 3.125 |  | Exterior Ground | 3 | Masonary
2022-03-22 | Water Bill (March) | 8.03 | SL3 | BWA |  | 1 | 74 |  | 74 |  | Yes | U |  |  |  |  | 8.032 |  | Administrative | 8 | Administrative
2022-03-23 | 20 X Corona Porcelain Tiles Nebraska Ivory 56.6x56.6 | 25.1 | FF19 | KooyMan |  | 1 | 339.8 |  | 339.8 |  | Yes | M |  |  |  |  | 25.165 |  | Tiling | 25 | Tiling
2022-03-23 | 280 X Corona Porcelain Tiles Nebraska Ivory 56.6x56.7 | 25.1 | FF19 | KooyMan |  | 1 | 4787.2 |  | 4787.2 |  | Yes | M |  |  |  |  | 25.17 |  | Tiling | 25 | Tiling
2022-03-24 | Tile Cement | 25.1 | FF19 | Carter & Company |  | 1 | 1237.65 |  | 1237.65 |  | Yes | M |  | 3-00062265 |  |  | 25.175 |  | Tiling | 25 | Tiling
2022-03-24 | Lumber | 7.9 | GL18 | Marshall's Trading |  | 1 | 603.93 |  | 603.93 |  | Yes | M |  |  |  |  | 7.98 |  | Roof Construction | 7 | Carpentry
2022-03-25 | Scaffold extension to 3/25 | 7.9 | GL18 | Williams Equiptment |  | 1 | 1102.16 |  | 1102.16 |  | Yes | U |  |  |  |  | 7.985 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-03-25 | Wire Transfer | 1.11 | Xfer | Sievewright Rogers |  | 1 | 50000 | -156.25 | 49843.75 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2022-03-30 | Electrical Supplies | 13.4 | GL18 | All Phase Electrical Supplies Inc |  | 1 | 5738.18 | 1004.18 | 6742.36 |  | Yes | M |  |  |  |  | 13.41 |  | Electrical Work | 13 | Electrical
2022-04-01 | 90 Degree Angle Brakets | 7.95 | FF16 | BRC West Indies |  | 1 | 71.24 |  | 71.24 |  | Yes | M |  |  |  |  | 7.9515 |  | Roof Construction | 7 | Carpentry
2022-04-02 | Misc Masonary supplies (Dianne Refund) | 3.8 | GL10 | Carter & Company |  | 1 | 337.26 | 59.0205 | 396.2805 | 958.05 | Yes | M |  | 810040778 |  |  | 3.815 |  | Exterior Ground | 3 | Masonary
2022-04-02 | Misc Masonary supplies (Dianne Refund) | 3.8 | GL10 | Carter & Company |  | 1 | 4.81 |  | 4.81 |  | Yes | M |  |  |  |  | 3.82 |  | Exterior Ground | 3 | Masonary
2022-04-02 | Misc Electrical supplies (Dianne Refund) | 13.38 | GL18 | Carter & Company |  | 1 | 478.1 | 83.6675 | 561.7675 |  | Inv | M |  | 810040778 |  |  |  |  | Electrical Work | 13 | Electrical
2022-04-02 | Masonary Services | 3.8 | GL18 | Ian Wiltshire |  | 1 | 10000 |  | 10000 |  | Yes | L |  |  |  |  | 3.825 |  | Exterior Ground | 3 | Masonary
2022-04-05 | Toilet services | 8.04 | EH0 | Infra Rentals |  | 1 | 605.5 |  | 605.5 |  | Yes | U |  |  |  |  | 8.041 |  | Administrative | 8 | Administrative
2022-04-05 | 50 X Corona Porcelain Tiles Nebraska Ivory 56.6x56.6 | 25.1 | FF19 | KooyMan |  | 1 | 964.45 |  | 964.45 |  | Yes | M |  |  |  |  | 25.16 |  | Tiling | 25 | Tiling
2022-04-06 | Misc Carpentry Supplies | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | 22.67 |  | 22.67 |  | Inv | M |  | MB-04062022 |  |  |  |  | Roof Construction | 7 | Carpentry
2022-04-06 | Misc Carpentry Supplies | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | 143.28 |  | 143.28 |  | Inv | M |  | MB-04062022 |  |  |  |  | Roof Construction | 7 | Carpentry
2022-04-06 | Misc Carpentry Supplies | 7.8 | FF15 | Modern Builders (Marlon) |  | 1 | 27.2 |  | 27.2 | 193.15 | Yes | M |  | MB-04062022 |  |  | 7.85 |  | Roof Construction | 7 | Carpentry
2022-04-06 | Permaclad and Roofing Supplies | 7.95 | FF16 | BRC West Indies |  | 1 | 2424.73 |  | 2424.73 |  | Yes | M |  |  |  |  | 7.9555 |  | Roof Construction | 7 | Carpentry
2022-04-06 | Building and installing decorative cap formwork for entrance Porch | 7.82 | FF19 | Modern Builders (Marlon) |  | 1 | 462 |  | 462 |  | Inv | L |  | 22040501 |  |  |  |  | FIRST FLOOR FORMWORK | 7 | Carpentry
2022-04-06 | Blocking up garage entrance (building and installing door) | 7.82 | FF19 | Modern Builders (Marlon) |  | 1 | 480 |  | 480 |  | Inv | L |  | 22040501 |  |  |  |  | Doors | 7 | Carpentry
2022-04-06 | Tiling first floor (payment on account) | 25.1 | FF19 | Modern Builders (Marlon) |  | 1 | 3150 |  | 3150 | 9037.1 | Yes | L |  | 22040501 |  |  | 25.135 |  | Tiling | 25 | Tiling
2022-04-06 | Erection of roof (97% complete) | 7.95 | GL11 | Modern Builders (Marlon) |  | 1 | 4255.1 |  | 4255.1 |  | Inv | L |  | 22040501 |  |  |  |  | Roof Construction | 7 | Carpentry
2022-04-06 | Building and installing door frames (90% complete) | 7.82 | GL8 | Modern Builders (Marlon) |  | 1 | 690 |  | 690 |  | Inv | L |  | 22040501 |  |  |  |  | Doors | 7 | Carpentry
2022-04-07 | 15 bags of ARAWAK CEMENT GREY 42.5K | 7.8 | FF19 | Carter & Company |  | 1 | 297.86 |  | 297.86 |  | Yes | M |  |  |  |  | 7.815 |  | Exterior Ground | 7 | Carpentry
2022-04-07 | Tiles | 25.1 | FF19 | Tile Hut |  | 1 | 12868.33 | 2251.96 | 15120.29 |  | Yes | M |  | 16951 |  |  | 25.11 |  | Tiling | 25 | Tiling
2022-04-07 | Construction Insurance for 2 months | 8.02 | FF19 | City Of Bridgetown |  | 2 | 344.2 |  | 688.4 |  | Yes | U |  |  |  |  | 8.021 |  | Administrative | 8 | Administrative
2022-04-14 | Misc Painting Supplies Reimburstment | 26.2 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 197.85 |  | 197.85 | 5647.85 | Yes | M |  | Des04142022 |  |  | 26.225 |  | Painting (Finishes & Trim) | 26 | Painting
2022-04-14 | Ceiling Trowel Plastic | 26.2 | GL18 | Desmond (Harclyde Bedford) |  | 1 | 5450 |  | 5450 |  | Inv | L |  | Des04142022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-04-16 | Non Sanded Grout | 25.1 | FF19 | Tile Hut |  | 1 | 31.46 | 5.5 | 36.96 |  | Yes | M |  |  |  |  | 25.11 |  | Painting (Finishes & Trim) | 25 | Tiling
2022-04-19 | Mixer Rental | 3.1 | GL11 | Brian Hinds |  | 1 | 350 |  | 350 |  | Yes | U |  |  |  |  | 3.12 |  | Exterior Ground | 3 | Masonary
2022-04-19 | Scaffolding extension (4/9 thru 5/6) | 7.9 | GL18 | Williams Equiptment |  | 1 | 1135.05 |  | 1135.05 |  | Yes | U |  |  |  |  | 7.915 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-04-19 | BL&P | 8.03 | SL3 | BL&P |  | 1 | 20.59 |  | 20.59 |  | Yes | U |  |  |  |  | 8.0335 |  | Exterior Ground | 8 | Administrative
2022-04-22 | ARAWAK CEMENT GREY 42.5K | 3.16 | FF19 | Carter & Company |  | 20 | 15.9 | 79.15 | 397.15 |  | Yes | M |  |  |  |  | 7.81 |  | Exterior Ground | 3 | Masonary
2022-04-22 | 6 meers of stone | 5.67 | GL11 | Shawn Grandison |  | 1 | 700 |  | 700 |  | Yes | M |  |  |  |  | 5.6725 |  | Exterior Ground | 5 | Earthworks
2022-04-23 | Nails and Misc Supplies | 3.06 | FF16 | Carter & Company |  | 1 | 69.14 |  | 69.14 |  | Yes | M |  |  |  |  | 3.063 |  | Exterior Ground | 3 | Masonary
2022-04-23 | Plywood | 3.06 | FF16 | Carter & Company |  | 1 | 93.68 |  | 93.68 |  | Yes | M |  |  |  |  | 3.0635 |  | Exterior Ground | 3 | Masonary
2022-04-23 | Masonary nails and Plywood | 3.8 | GL18 | Carter & Company |  | 1 | 162.82 |  | 162.82 | 262.7 | Yes | M |  |  |  |  | 3.815 |  | Exterior Ground | 3 | Masonary
2022-04-25 | Hilti to level ground floor | 7.9 | GL18 | Williams Equiptment |  | 1 | 99.88 |  | 99.88 |  | Yes | U |  |  |  |  | 7.91 |  | Ground Floor Slab | 7 | Carpentry
2022-04-27 | Masonary Steel | 3.8 | GL18 | Carter & Company |  | 1 | 653.65 |  | 653.65 |  | Yes | M |  |  |  |  | 3.82 |  | Exterior Ground | 3 | Masonary
2022-04-30 | Metal Cutting Disk & Fibers | 3.8 | GL18 | Carter & Company |  | 1 | 105.91 |  | 105.91 |  | Yes | M |  |  |  |  | 3.825 |  | Exterior Ground | 3 | Masonary
2022-04-30 | BWA Payment | 8.03 | SL3 | BWA |  | 1 | 78.5 |  | 78.5 |  | Yes | U |  |  |  |  | 8.033 |  | Exterior Ground | 8 | Administrative
2022-05-05 | Lumber | 7.8 | FF15 | Carter & Company |  | 1 | 665 | 116.375 | 781.375 |  | Yes | M |  |  |  |  | 7.82 |  | Exterior Ground | 7 | Carpentry
2022-05-05 | Electrical Fixtures | 13.4 | GL18 | Carter & Company |  | 1 | 216.86 | 37.9505 | 254.8105 |  | Yes | M |  |  |  |  | 13.415 |  | Electrical Work | 13 | Electrical
2022-05-05 | Steel Rebar | 3.8 | GL18 | Carter & Company |  | 1 | 200 | 35 | 235 |  | Yes | M |  |  |  |  | 3.81 |  | Exterior Ground | 3 | Masonary
2022-05-05 | Plumbing | 10.38 | GL19 | Carter & Company |  | 1 | 500 | 87.5 | 587.5 |  | Yes | M |  |  |  |  | 10.3825 |  | Plumbing | 10 | Plumbing
2022-05-05 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 42000 | -131.25 | 41868.75 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2022-05-10 | ARAWAK CEMENT GREY 42.5K | 3.16 | FF19 | Carter & Company |  | 1 | 297.86 |  | 297.86 |  | Yes | M |  |  |  |  | 3.163 |  | Exterior Ground | 3 | Masonary
2022-05-10 | Mortar Admix | 3.8 | GL10 | Carter & Company |  | 1 | 24.98 | 4.37 | 29.35 |  | Yes | M |  |  | SR In Store |  | 3.81 |  | Fixtures & Fittings | 3 | Masonary
2022-05-10 | Scaffolding extension (thru 5/20) | 7.9 | GL18 | Williams Equiptment |  | 1 | 378.35 |  | 378.35 |  | Yes | U |  |  |  |  | 7.91 |  | Exterior Ground | 7 | Carpentry
2022-05-11 | Plate compactor (1 day) | 5.64 | EH0 | Williams Equiptment |  | 1 | 141 |  | 141 | 519.35 | Yes | U |  |  |  |  | 5.644 |  | Exterior Ground | 5 | Earthworks
2022-05-11 | Well Rings | 3.8 | GL10 | Barbados Steel Works |  | 5 | 26 |  | 130 |  | Yes | M |  |  | SR In Store |  | 3.815 |  | Fixtures & Fittings | 3 | Masonary
2022-05-12 | Well Rings | 3.8 | GL10 | Barbados Steel Works |  | 1 | 26 |  | 26 |  | Yes | M |  |  | SR In Store |  | 3.82 |  | Fixtures & Fittings | 3 | Masonary
2022-05-13 | Desil & Hilti Use | 3.8 | GL18 | Ian Wiltshire |  | 1 | 500 |  | 500 |  | Yes | M |  | 472602 |  |  | 3.845 |  | Fixtures & Fittings | 3 | Masonary
2022-05-13 | Biscuit Grout | 25.1 | GL18 | Tile Hut |  | 2 | 30.6 | 5.355 | 66.555 |  | Yes | M |  |  | SR In Store |  | 25.125 |  | Tiling | 25 | Tiling
2022-05-14 | Pine for Cabinets and Closets | 7.7 | GL18 | Carter & Company |  | 30 | 109.9 | 576.975 | 3873.975 |  | Inv | M |  | 3-00065687 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-05-14 | Pine for Cabinets and Closets | 7.7 | GL18 | Carter & Company |  | 8 | 94.4725 | 132.2615 | 888.0415 |  | Inv | M |  | 3-00065687 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-05-14 | Handling Charge | 7.7 | GL18 | Carter & Company |  | 1 | 10 | 1.64 | 11.64 | 4773.66 | Yes | M |  | 3-00065687 |  |  | 7.72 |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-05-14 | Hex XL Calacatta Goldmatte Mosiac Tiles | 25.1 | GL18 | Terrific Tiles |  | 6 | 26.64 | 27.972 | 187.812 |  | Yes | M |  |  | SR In Store |  | 25.13 |  | Tiling | 25 | Tiling
2022-05-14 | Hex XL Calacatta Goldmatte Mosiac Tiles | 25.1 | GL18 | Terrific Tiles |  | 1 | 26.64 | 4.662 | 31.302 |  | Yes | M |  |  | SR In Store |  | 25.135 |  | Tiling | 25 | Tiling
2022-05-14 | Pine for Cabinets and Closets | 7.7 | GL18 | Marshall's Trading |  | 1 | 2702.21 |  | 2702.21 |  | Yes | M |  | 3-00065687 |  |  | 7.71 |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-05-16 | Residenza Rapollano Pol Shiny 30x60cm Tiles | 25.1 | GL18 | Keystone |  | 420 | 3.37 | 255.14 | 1670.54 |  | Yes | M |  | 472604 |  |  | 25.11 |  | Tiling | 25 | Tiling
2022-05-16 | Delivery Residenza Rapollano Pol Shiny 30x60cm Tiles | 25.1 | GL18 | Keystone |  | 1 | 42.55 |  | 42.55 |  | Yes | M |  | 472604 |  |  | 25.115 |  | Tiling | 25 | Tiling
2022-05-18 | Masonary & Concrete Nails | 3.8 | GL10 | KooyMan |  | 1 | 19.55 | 3.4213 | 22.9713 |  | Inv | M |  | 69754 | SR In Store |  |  |  | Exterior Ground | 3 | Masonary
2022-05-18 | Pine for Boxing | 7.7 | GL18 | Carter & Company |  | 1 | 451.76 |  | 451.76 |  | Yes | M |  |  |  |  | 7.74 |  | Exterior Ground | 7 | Carpentry
2022-05-18 | 8 x PVC Tilestrip Jasmin | 25.1 | GL18 | KooyMan |  | 1 | 102.06 | 17.8605 | 119.9205 | 142.89 | Yes | M |  | 69754 | SR In Store |  | 25.115 |  | Tiling | 25 | Tiling
2022-05-19 | A98 BRC Fabrics | 3.8 | GL10 | Carter & Company |  | 1 | 736.62 |  | 736.62 |  | Yes | M |  |  |  |  | 3.835 |  | Exterior Ground | 3 | Masonary
2022-05-19 | Sandless white grout | 25.1 | GL18 | Carter & Company |  | 1 | 22.16 | 3.878 | 26.038 |  | Yes | M |  |  | SR In Store |  | 25.11 |  | Tiling | 25 | Tiling
2022-05-19 | Matt Silver roundTile Strips (returned) | 25.1 | GL18 | Tile Hut |  | 1 | 0 | 0 | 0 |  | Yes | M |  |  | SR In Store |  | 25.115 |  | Tiling | 25 | Tiling
2022-05-20 | Tile Cement | 25.1 | GL18 | Carter & Company |  | 1 | 1090.05 |  | 1090.05 |  | Yes | M |  |  |  |  | 25.145 |  | Tiling | 25 | Tiling
2022-05-23 | Erection of roof (97% complete) | 7.95 | GL11 | Modern Builders (Marlon) |  | 1 | 750.9 |  | 750.9 |  | Inv | L |  | 22051901 |  |  |  |  | Roof Construction | 7 | Carpentry
2022-05-23 | Tiling floor areas (payment on account) | 25.1 | GL18 | Modern Builders (Marlon) |  | 1 | 3400 |  | 3400 | 9158.7 | Yes | L |  | 22051901 |  |  | 25.165 |  | Tiling | 25 | Tiling
2022-05-23 | Erecting decking and side formwork for Apartment deck and under stair storage (90% complete) | 7.38 | GL6 | Modern Builders (Marlon) |  | 1 | 1657.8 |  | 1657.8 |  | Inv | L |  | 22051901 |  |  |  |  | Exterior Ground | 7 | Carpentry
2022-05-23 | Erection of formwork for suspended stairs, apartment stairs and stairs leading from parking bay | 7.38 | GL6 | Modern Builders (Marlon) |  | 1 | 3350 |  | 3350 |  | Inv | L |  | 22051901 |  |  |  |  | Exterior Ground | 7 | Carpentry
2022-05-24 | Masonary Steel | 3.8 | GL10 | Carter & Company |  | 1 | 182.1 | 31.8675 | 213.9675 |  | Inv | M |  | 3-00066422 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-05-24 | ARAWAK CEMENT GREY 42.5K | 3.8 | GL10 | Carter & Company |  | 1 | 238.5 | 41.7375 | 280.2375 |  | Inv | M |  | 3-00066422 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-05-24 | Handling Charge | 3.8 | GL10 | Carter & Company |  | 1 | 10 | 1.75 | 11.75 |  | Inv | M |  | 3-00066422 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-05-24 | Handling Charge Cement | 3.8 | GL10 | Carter & Company |  | 1 | 15 | 2.625 | 17.625 | 975.06 | Yes | M |  | 3-00066422 |  |  | 3.895 |  | Exterior Ground | 3 | Masonary
2022-05-24 | MiscElectrical | 13.41 | GL18 | Carter & Company |  | 1 | 296.95 | 51.9662 | 348.9162 |  | Inv | M |  | 3-00066422 |  |  |  |  | Exterior Ground | 13 | Electrical
2022-05-24 | MiscElectrical | 13.41 | GL18 | Carter & Company |  | 1 | 87.29 | 15.2757 | 102.5657 |  | Inv | M |  | 3-00066422 |  |  |  |  | Exterior Ground | 13 | Electrical
2022-05-25 | Barbados Light & Power | 8.04 | GL11 | BL&P |  | 1 | 21.37 |  | 21.37 |  | Yes | U |  |  |  |  | 8.0411 |  | Exterior Ground | 8 | Administrative
2022-05-25 | Water | 8.04 | GL11 | BWA |  | 1 | 80.2 |  | 80.2 |  | Yes | U |  |  |  |  | 8.0412 |  | Exterior Ground | 8 | Administrative
2022-05-25 | 8 x PVC Tilestrip Jasmin (Returned) | 25.1 | GL18 | KooyMan |  | -1 | 102.06 | -17.8605 | -119.9205 |  | Yes | M |  |  | SR In Store |  | 25.12 |  | Tiling | 25 | Tiling
2022-05-26 | Concrete for exterior ground | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | 12647.7 |  | 12647.7 |  | Yes | M |  |  |  |  | 3.061 |  | Exterior Ground | 3 | Masonary
2022-05-26 | Labor for exterior ground concrete | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | 2220 |  | 2220 |  | Yes | L |  |  |  |  | 3.061 |  | Exterior Ground | 3 | Masonary
2022-05-27 | 2 Fence Poles for Car Park | 9.1 | EH0 | DAJ Manufacturing |  | 1 | 68.71 |  | 68.71 |  | Yes | M |  |  |  |  | 9.11 |  | Painting (Finishes & Trim) | 9 | 0
2022-05-27 | Termite treatment for driveway and stairs. | 3.06 | FF16 | Greens's Exterminating & Fencing |  | 1 | 822.5 |  | 822.5 |  | Yes | M |  |  |  |  | 3.061 |  | Exterior Ground | 3 | Masonary
2022-05-27 | Props for 3 weeks as per email. | 3.06 | FF16 | Williams Equiptment |  | 1 | 373.65 |  | 373.65 |  | Yes | M |  |  |  |  | 3.0615 |  | Exterior Ground | 3 | Masonary
2022-05-27 | Patio Painting Supplies | 26.2 | GL10 | Carter & Company |  | 1 | 1027.81 |  | 1027.81 |  | Yes | M |  |  |  |  | 26.22 |  | Painting (Finishes & Trim) | 26 | Painting
2022-06-01 | Concrete Overage | 3.06 | FF16 | Rayside Construction Ltd |  | 1 | 748.48 |  | 748.48 |  | Yes | M |  |  |  |  | 3.061 |  | Exterior Ground | 3 | Masonary
2022-06-02 | Misc Masonary supplies (Dianne Refund) | 3.06 | FF16 | Marshall's Trading |  | 1 | 54.85 | 9.5987 | 64.4488 |  | Yes | M |  |  |  |  | 3.0675 |  | Exterior Ground | 3 | Masonary
2022-06-02 | Scaffolding Extension | 7.9 | GL18 | Williams Equiptment |  | 1 | 351.32 |  | 351.32 |  | Yes | U |  |  |  |  | 7.94 |  | Exterior Ground | 7 | Carpentry
2022-06-02 | the labor cost for the work done at the front was done is$2550 includes the 4step and the rest of the boxing work. | 3.8 | GL18 | Desmond (Harclyde Bedford) |  | 1 | 2550 |  | 2550 |  | Yes | L |  |  |  |  | 3.85 |  | Paraphet and front porch Design construction | 3 | Masonary
2022-06-02 | Funds Transfervfor Construction | 1.11 | Xfer | Marcia Rogers |  | 1 | 51000 | -159.37 | 50840.63 |  | Yes | X |  |  |  |  | 7.94 |  | Administrative | 1 | Transfers
2022-06-03 | Toilet services | 8.04 | EH0 | Infra Rentals |  | 1 | 897.7 |  | 897.7 |  | Yes | U |  |  |  |  | 8.0455 |  | Exterior Ground | 8 | Administrative
2022-06-04 | Misc Masonary supplies (Dianne Refund) | 3.06 | FF16 | Carter & Company |  | 1 | 277.4925 |  | 277.4925 | 805.89 | Yes | M |  | 3-00067323 |  |  | 3.0665 |  | Exterior Ground | 3 | Masonary
2022-06-04 | Nmasonary Nails | 3.06 | FF16 | Carter & Company |  | 1 | 17.43 | 3.0502 | 20.4802 |  | Yes | M |  |  |  |  | 3.068 |  | Exterior Ground | 3 | Masonary
2022-06-04 | Masonary Services | 3.06 | FF16 | Ian Wiltshire |  | 1 | 6200 |  | 6200 |  | Yes | L |  |  |  |  | 3.061 |  | Foundation Extras Work | 3 | Masonary
2022-06-04 | Masonary Services | 3.06 | FF16 | Ian Wiltshire |  | 1 | 3800 |  | 3800 |  | Yes | L |  |  |  |  | 3.0615 |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-06-04 | Tile Cement | 25.1 | GL18 | Carter & Company |  | 15 | 29.98 | 78.6975 | 528.3975 |  | Inv | M |  | 3-00067323 |  |  |  |  | Tiling | 25 | Tiling
2022-06-04 | Misc Supplies (Refunded to Marlon) | 13.41 | GL18 | Marlon |  | 1 | 84.93 |  | 84.93 |  | Yes | M |  |  |  |  | 13.417 |  | Exterior Ground | 13 | Electrical
2022-06-11 | Misc Masonary supplies (Dianne Refund) | 3.06 | GL18 | Carter & Company |  | 1 | 405.57 |  | 405.57 |  | Yes | M |  |  |  |  | 3.064 |  | Exterior Ground | 3 | Masonary
2022-06-13 | Tiling floor areas (payment on account) | 25.1 | FF19 | Modern Builders (Marlon) |  | 1 | 6250 |  | 6250 |  | Inv | L |  | 22060901 |  |  |  |  | Tiling | 25 | Tiling
2022-06-13 | Building Closets (payment on account) | 3.06 | FF19 | Modern Builders (Marlon) |  | 1 | 2500 |  | 2500 | 8934.2 | Yes | L |  | 22060901 |  |  | 3.063 |  | Interior Outfittings and Schedules Design | 3 | Masonary
2022-06-13 | Drawer Slides (Undermount Soft Closing Drawer Slides 16" & 18") | 3.06 | FF19 | Xclusive Products Inc. |  | 1 | 738.58 |  | 738.58 |  | Yes | M |  |  |  |  | 3.0635 |  | Interior Outfittings and Schedules Design | 3 | Masonary
2022-06-13 | Erecting decking and side formwork for Apartment deck and under stair storage (100% complete) | 3.06 | GL18 | Modern Builders (Marlon) |  | 1 | 184.2 |  | 184.2 |  | Inv | L |  | 22060901 |  |  |  |  | Exterior Ground | 3 | Masonary
2022-06-14 | Additional Tiles | 25.1 | GL18 | Tile Hut |  | 1 | 3262.5 |  | 3262.5 |  | Yes | M |  |  |  |  | 25.145 |  | Tiling | 25 | Tiling
2022-06-14 | Additional Tiles | 25.1 | GL18 | Tile Hut |  | 1 | 391.59 |  | 391.59 |  | Yes | M |  |  |  |  | 25.15 |  | Tiling | 25 | Tiling
2022-06-15 | 8" Blocks | 25.1 | GL18 | Ready Block |  | 1 | 1001.1 |  | 1001.1 |  | Yes | M |  |  |  |  | 25.155 |  | Exterior Ground | 25 | Tiling
2022-06-17 | Misc Masonary supplies (Dianne Refund) | 3.06 | FF16 | Carter & Company |  | 1 | 1778.42 | 311.2235 | 2089.6435 |  | Yes | M |  |  |  |  | 3.0635 |  | Exterior Ground | 3 | Masonary
2022-06-20 | Carpentry Supplies | 7.71 | FF16 | Carter & Company |  | 1 | 222.93 | 39.0127 | 261.9427 |  | Yes | M |  |  |  |  | 7.713 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-20 | Gym Tiles | 25.1 | GL18 | KooyMan |  | 1 | 2068.8 |  | 2068.8 |  | Yes | M |  |  |  |  | 25.14 |  | Tiling | 25 | Tiling
2022-06-21 | Electric Supply | 8.04 | GL11 | BL&P |  | 1 | 23.77 |  | 23.77 |  | Yes | M |  |  |  |  | 8.0445 |  | Administrative | 8 | Administrative
2022-06-21 | Mixer Use | 3.1 | GL11 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | M |  |  |  |  | 3.15 |  | Exterior Ground | 3 | Masonary
2022-06-23 | Building Closets (65% complete) | 3.06 | FF19 | Modern Builders (Marlon) |  | 1 | 4357.5 |  | 4357.5 |  | Inv | L |  | 22062301 |  |  |  |  | Wardrobes, Vanities & laundry Units | 3 | Masonary
2022-06-23 | Tiling floor areas (payment on account) | 25.1 | GL18 | Modern Builders (Marlon) |  | 1 | 2200 |  | 2200 |  | Inv | L |  | 22062301 |  |  |  |  | Tiling | 25 | Tiling
2022-06-23 | Tiling bathroom wall areas (65%) | 25.1 | GL18 | Modern Builders (Marlon) |  | 1 | 3198 |  | 3198 | 11690.5 | Yes | L |  | 22062301 |  |  | 25.17 |  | Tiling | 25 | Tiling
2022-06-23 | Building Kitchen cubpboards (25% complete) | 7.7 | GL19 | Modern Builders (Marlon) |  | 1 | 1935 |  | 1935 |  | Inv | L |  | 22062301 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-24 | Carpentry Supplies | 7.71 | FF16 | Modern Builders (Marlon) |  | 1 | 300.93 |  | 300.93 |  | Yes | M |  |  |  |  | 7.712 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-24 | Carpentry Supplies | 7.71 | FF16 | Marshall's Trading |  | 1 | 38.99 |  | 38.99 |  | Yes | M |  |  |  |  | 7.7125 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-25 | Masonary Supplies | 3.06 | FF16 | Carter & Company |  | 1 | 105.83 | 18.5202 | 124.3502 |  | Yes | M |  |  |  |  | 3.0615 |  | Exterior Ground | 3 | Masonary
2022-06-25 | Water Supply | 8.04 | GL11 | BWA |  | 1 | 79.57 |  | 79.57 |  | Yes | U |  |  |  |  | 8.048 |  | Administrative | 8 | Administrative
2022-06-28 | Honduras Pine | 7.71 | GL19 | Carter & Company |  | 1 | 924.33 | 161.7577 | 1086.0878 |  | Yes | M |  |  |  |  | 7.711 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-30 | 1/2 inch Hondurus Pine Ply | 7.7 | GL18 | Carter & Company |  | 1 | 105.81 |  | 105.81 |  | Yes | M |  |  |  |  | 7.71 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-06-30 | Backsplash & Shower Bottom Tiles | 25.1 | GL18 | Terrific Tiles |  | 1 | 870.2 | 152.285 | 1022.485 |  | Yes | M |  |  |  |  | 25.175 |  | Tiling | 25 | Tiling
2022-06-30 | Scaffolding Extension | 7.9 | GL18 | Williams Equiptment |  | 1 | 756.7 |  | 756.7 |  | Yes | M |  |  |  |  | 7.91 |  | Exterior Ground | 7 | Carpentry
2022-07-01 | Barbados Customs | 13.4 | GL18 | Barbados Customs |  | 1 | 75.6 |  | 75.6 |  | Yes | M |  |  |  |  | 13.415 |  | Fixtures & Fittings | 13 | Electrical
2022-07-01 | Air Freight for Electrical lights | 13.4 | GL18 | Skyline Cargo Ltd |  | 1 | 25.25 |  | 25.25 |  | Yes | M |  |  |  |  | 13.42 |  | Fixtures & Fittings | 13 | Electrical
2022-07-01 | Trowel Plastic | 26.52 | SL 17 | Trowel Plastic |  | 1 | 2498.12 |  | 2498.12 |  | Yes | M |  |  |  |  | 26.525 |  | Painting (Finishes & Trim) | 26 | Painting
2022-07-02 | Arawak Cement GREY 42.5K & Steel | 3.06 | SL5 | Carter & Company |  | 1 | 684.13 |  | 684.13 |  | Yes | M |  |  |  |  | 3.062 |  | Guard Wall Extras | 3 | Masonary
2022-07-04 | 1-1/4 12X 14 Wood | 7.7 | GL18 | Carter & Company |  | 1 | 1050.58 |  | 1050.58 |  | Yes | M |  |  |  |  | 7.715 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-05 | Kingslide Undermount with Clips | 25.1 | GL18 | Island Tiles |  | 1 | 159 | 27.825 | 186.825 |  | Yes | M |  |  |  |  | 25.125 |  | Tiling | 25 | Tiling
2022-07-05 | Drawer Slides EXT Umount | 25.1 | GL18 | Exotic Woods |  | 1 | 553.84 | 96.922 | 650.762 |  | Yes | M |  |  |  |  | 25.13 |  | Kitchen & Pantry Cupboards | 25 | Tiling
2022-07-07 | Nails | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 19.47 |  | 19.47 |  | Yes | M |  | MB07072022 |  |  | 7.76 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-07 | Screws ) | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 42.3 |  | 42.3 |  | Yes | M |  | MB07072023 |  |  | 7.765 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-07 | Screws ) | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 102.07 |  | 102.07 |  | Yes | M |  | MB07072024 |  |  | 7.77 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-07 | Floor Drain | 10.38 | GL18 | Modern Builders (Marlon) |  | 1 | 160.25 |  | 160.25 |  | Yes | M |  | MB07072025 |  |  | 10.3875 |  | Plumbing | 10 | Plumbing
2022-07-07 | Kreg Screws | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 38.99 |  | 38.99 |  | Yes | M |  | MB07072026 |  |  | 7.78 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-08 | Concrete Blocks | 7.9 | GL18 | Ready Block |  | 1 | 443.86 |  | 443.86 |  | Yes | M |  |  |  |  | 7.935 |  | Exterior Ground | 7 | Carpentry
2022-07-11 | Misc Tiling Supplies | 25.1 | GL18 | Carter & Company |  | 1 | 703.83 |  | 703.83 |  | Yes | M |  |  |  |  | 7.795 |  | Tiling | 25 | Tiling
2022-07-11 | Arawak Cement | 3.06 | SL5 | Carter & Company |  | 1 | 238.29 |  | 238.29 |  | Yes | M |  |  |  |  | 3.069 |  | Exterior Ground | 3 | Masonary
2022-07-11 | Funds Transfervfor Construction | 1.11 | Xfer | Marcia Rogers |  | 1 | 54000 | -168.75 | 53831.25 |  | Yes | X |  |  |  |  | 7.78 |  | Administrative | 1 | Transfers
2022-07-12 | Tile Cement | 25.1 | GL18 | Carter & Company |  | 1 | 449.7 | 78.6975 | 528.3975 |  | Inv | M |  | 3-00069948 |  |  |  |  | Tiling | 25 | Tiling
2022-07-12 | Masomary Nails | 3.8 | GL18 | Carter & Company |  | 1 | 13.01 | 2.2767 | 15.2867 |  | Inv | M |  | 3-00069948 |  |  |  |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-12 | Plywood | 3.8 | GL18 | Carter & Company |  | 1 | 126.29 | 22.1008 | 148.3907 |  | Inv | M |  | 3-00069948 |  |  |  |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-12 | Handling Charge | 3.8 | GL18 | Carter & Company |  | 1 | 10 | 1.75 | 11.75 | 703.82 | Yes | M |  | 3-00069948 |  |  | 3.825 |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-12 | Building Kitchen cubpboards (70% complete) | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 3483 |  | 3483 |  | Inv | L |  | 22070701 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-12 | Building Closets (75% complete) | 7.7 | GL18 | Modern Builders (Marlon) |  | 1 | 1055 |  | 1055 |  | Inv | L |  | 22070701 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-07-12 | Tiling floor areas (payment on account) | 25.1 | GL18 | Modern Builders (Marlon) |  | 1 | 1800 |  | 1800 |  | Inv | L |  | 22070701 |  |  |  |  | Tiling | 25 | Tiling
2022-07-12 | Tiling bathroom wall areas (90%) | 25.1 | GL18 | Modern Builders (Marlon) |  | 1 | 1230 |  | 1230 | 7568 | Yes | L |  | 22070701 |  |  | 7.755 |  | Tiling | 25 | Tiling
2022-07-12 | Masonary Survices (Exterior Gardens & Pavement Extras) | 3.8 | GL18 | Ian Wiltshire |  | 1 | 10000 |  | 10000 |  | Yes | L |  |  |  |  | 3.81 |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-14 | Eletrical Supplies | 8.04 | GL10 | All Phase Electrical Supplies Inc |  | 1 | 2368.66 | 414.5155 | 2783.1755 |  | Yes | M |  |  |  |  | 8.0455 |  | Electrical Work | 8 | Administrative
2022-07-15 | Downpayment on Cabinetry Face Build 50% | 7.7 | GL18 | Roger Forde |  | 1 | 1259 |  | 1259 |  | Yes | L |  |  |  |  | 7.75 |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-07-17 | 12 bags of cement | 3.8 | GL10 | Carter & Company |  | 1 | 238.29 |  | 238.29 |  | Yes | M |  |  |  |  | 3.865 |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-18 | Painting Supplies | 26.2 | GL10 | Carter & Company |  | 1 | 582.35 |  | 582.35 |  | Yes | M |  |  |  |  | 26.26 |  | Painting (Finishes & Trim) | 26 | Painting
2022-07-18 | Complete painting of faceboard | 26.41 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 1600 |  | 1600 |  | Yes | L |  |  |  |  | 26.417 |  | Painting (Finishes & Trim) | 26 | Painting
2022-07-18 | Complete installation of guttering | 26.5 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 2600 |  | 2600 | 4200 | Yes | L |  |  |  |  | 26.575 |  | Painting (Finishes & Trim) | 26 | Painting
2022-07-18 | BL&P | 8.04 | GL11 | BL&P |  | 1 | 30.94 |  | 30.94 |  | Yes | U |  |  |  |  | 8.048 |  | Administrative | 8 | Administrative
2022-07-20 | Tiles | 25.1 | GL10 | Tile Hut |  | 1 | 222.18 | 38.8815 | 261.0615 |  | Inv | M |  | TH-07202022 |  |  |  |  | Tiling | 25 | Tiling
2022-07-20 | Countertop slab | 7.7 | GL10 | Tile Hut |  | 2 | 761.7 | 266.595 | 1789.995 |  | Inv | M |  | TH-07202022 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-20 | Handling Charge | 7.7 | GL10 | Tile Hut |  | 1 | 76.6 | 13.405 | 90.005 | 2141.06 | Yes | M |  | TH-07202022 |  |  | 7.72 |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-20 | Recessed lighting 4" | 13.38 | SL 17 | Kooyman |  | 1 | 182.86 | 0 | 182.86 |  | Yes | M |  |  |  |  | 13.381 |  | Electrical Work | 13 | Electrical
2022-07-21 | 8 bags of Cement | 3.8 | GL10 | Carter & Company |  | 1 | 168.54 |  | 168.54 |  | Yes | M |  |  |  |  | 3.825 |  | Exterior Gardens & Pavement Extras | 3 | Masonary
2022-07-22 | S/Close Hinges | 7.7 | SL 17 | Carter & Company |  | 1 | 188.48 | 32.984 | 221.464 |  | Yes | M |  |  |  |  | 7.715 |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-07-22 | S/Close Hinges | 7.7 | SL 17 | Carter & Company |  | 1 | 42.56 | 7.448 | 50.008 |  | Yes | M |  |  |  |  | 7.72 |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-07-22 | Trowel Plastic (interior paints) 50% | 26.52 | SL 17 | Trowel Plastic |  | 1 | 3122.64 |  | 3122.64 |  | Yes | M |  |  |  |  | 26.523 |  | Painting (Finishes & Trim) | 26 | Painting
2022-07-23 | Returned Tiles | 25.1 | GL10 | Tile Hut |  | 1 | -31.74 | -5.5545 | -37.2945 |  | Inv | M |  | TH-07232022 |  |  |  |  | Tiling | 25 | Tiling
2022-07-23 | Returned Quartz | 7.7 | GL10 | Tile Hut |  | 1 | -1523.4 | -266.595 | -1789.995 |  | Inv | M |  | TH-07232022 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-23 | Quartz Slab (Snow White) | 7.7 | GL10 | Tile Hut |  | 2 | 1953.19 | 683.6165 | 4589.9965 |  | Inv | M |  | TH-07232022 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-23 | Delivery charge | 7.7 | GL10 | Tile Hut |  | 2 | 76.6 | 26.8 | 180 | 2942.71 | Yes | M |  | TH-07232022 |  |  | 7.725 |  | Administrative | 7 | Carpentry
2022-07-26 | Mixer Use | 3.1 | GL11 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | U |  |  |  |  | 3.11 |  | Exterior Ground | 3 | Masonary
2022-07-27 | Pine for Balcony rails | 7.7 | GL10 | Carter & Company |  | 1 | 1631.82 |  | 1631.82 |  | Yes | M |  |  |  |  | 7.735 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-07-28 | Tiling stairs (70% complete) | 25.1 | GL10 | Modern Builders (Marlon) |  | 1 | 1701 |  | 1701 |  | Inv | L |  | 22073801A |  |  |  |  | Tiling | 25 | Tiling
2022-07-28 | Electrical conduit extensions (100 % complete) | 8.04 | GL10 | Modern Builders (Marlon) |  | 1 | 720 |  | 720 |  | Inv | L |  | 22073801A |  |  |  |  | Electrical Work (Conduit extensions) | 8 | Administrative
2022-07-28 | Electrical circuit wiring (50% complete) | 8.04 | GL10 | Modern Builders (Marlon) |  | 1 | 4790 |  | 4790 |  | Inv | L |  | 22073801A |  |  |  |  | Electrical Work (Circuit Wiring) | 8 | Administrative
2022-07-28 | July Water bill | 8.04 | GL11 | BWA |  | 1 | 79.13 |  | 79.13 |  | Yes | M |  |  |  |  | 8.0445 |  | Administrative | 8 | Administrative
2022-07-28 | Scaffolding Extension refund | 7.9 | GL18 | Williams Equiptment |  | 1 | -54.05 |  | -54.05 |  | Yes | M |  |  |  |  | 7.94 |  | First Floor Walls | 7 | Carpentry
2022-07-28 | Building and installing door frames (100 % complete) | 7.82 | GL8 | Modern Builders (Marlon) |  | 1 | 460 |  | 460 | 10274 | Yes | L |  | 22073801A |  |  | 7.824 |  | Doors | 7 | Carpentry
2022-07-28 | Building Kitchen cubpboards (90% complete) | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 1548 |  | 1548 |  | Inv | L |  | 22073801A |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-07-28 | Building Closets (75% complete) | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 1055 |  | 1055 |  | Inv | L |  | 22073801A |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-01 | Toilets $1,362 ($1,292+$70 delivery to be paid separately) | 10.38 | GL10 | Barbados Steel Works |  | 1 | 1362 |  | 1362 |  | Yes | M |  |  |  |  | 10.381 |  | Interior Outfittings and Schedules Design | 10 | Plumbing
2022-08-03 | Construction of Vanities Deposit | 7.7 | GL11 | Modern Builders (Marlon) |  | 1 | 2615 |  | 0 |  | Yes | L |  |  |  |  | 7.715 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-03 | Final payment on Kitchen Cabinetry Face Build | 7.7 | GL18 | Roger Forde |  | 1 | 1259 |  | 1259 |  | Yes | L |  |  |  |  | 7.71 |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-08-03 | believe these are rail related. Order was broken up based on who had what. | 7.7 | SL 17 | L G Lumber Hardware Inc |  | 1 | 593.25 |  | 593.25 |  | Yes | M |  |  |  |  | 7.75 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-03 | $1,054.90 wood from Marshall's Trading. | 7.7 | SL 17 | Marshall's Trading |  | 1 | 1054.9 |  | 1054.9 |  | Yes | M |  |  |  |  | 7.755 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-03 | Refund to Marlon for supplies | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 228.2 |  | 228.2 |  | Yes | M |  |  |  |  | 7.76 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-03 | Refund to Marlon for supplies | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 111.28 |  | 111.28 |  | Yes | M |  |  |  |  | 7.765 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-03 | Mobilisation deposit for supplying and installation of vanity countertops | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 1315 |  | 1315 |  | Inv | L |  | 22080301 |  |  |  |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-08-03 | Mobilisation deposit for supplying and installation of vanity countertops | 7.7 | SL 17 | Modern Builders (Marlon) |  | 1 | 1300 |  | 1300 | 2615 | Yes | M |  | 22080301 |  |  | 7.72 |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-08-03 | Funds Transfervfor Construction | 1.11 | Xfer | Sievewright Rogers |  | 1 | 1800 |  | 1800 |  | Yes | X |  |  |  |  | 7.824 |  | Administrative | 1 | Transfers
2022-08-04 | Lumber Supplies (Pine) | 7.7 | GL11 | Carter & Company |  | 1 | 316.1 |  | 316.1 |  | Yes | M |  |  |  |  | 7.71 |  | Painting (Finishes & Trim) | 7 | Carpentry
2022-08-05 | Toilet Services thru August | 8.04 | EH0 | Infra Rentals |  | 2 | 305.5 |  | 611 |  | Yes | U |  |  |  |  | 8.042 |  | Exterior Ground | 8 | Administrative
2022-08-05 | Eletrical Supplies | 13.4 | GL18 | Modern Builders (Marlon) |  | 1 | 486.92 |  | 486.92 |  | Yes | M |  |  |  |  | 13.425 |  | Electrical Work (Circuit Wiring) | 13 | Electrical
2022-08-06 | Grout | 25.1 | GL11 | Tile Hut |  | 1 | 35.96 |  | 35.96 |  | Yes | M |  |  |  |  | 7.735 |  | Tiling | 25 | Tiling
2022-08-06 | Electrical Supplies | 13.4 | GL18 | All Phase Electrical Supplies Inc |  | 1 | 1301.5 |  | 1301.5 |  | Yes | M |  |  |  |  | 13.44 |  | Electrical Work (Circuit Wiring) | 13 | Electrical
2022-08-06 | Trowel Plastic Delivery charge | 26.52 | SL 17 | Trowel Plastic |  | 1 | 120 |  | 120 |  | Yes | M |  |  |  |  | 26.5245 |  | Painting (Finishes & Trim) | 26 | Painting
2022-08-08 | LED light bulbs | 13.4 | GL18 | Carter & Company |  | 1 | 209.37 |  | 209.37 |  | Yes | M |  |  |  |  | 13.43 |  | Fixtures & Fittings | 13 | Electrical
2022-08-11 | Painting Services (drawdown of $3500.00 for the two patios on the north side as they were finish) | 26.5 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 3500 |  | 3500 |  | Yes | L |  |  |  |  | 26.517 |  | Painting (Finishes & Trim) | 26 | Painting
2022-08-11 | Tiling Supplies | 25.1 | GL11 | Tile Hut |  | 1 | 444.43 |  | 444.43 |  | Yes | M |  |  |  |  | 7.755 |  | Tiling | 25 | Tiling
2022-08-11 | Lumber Supplies (9 pieces Pine) (Railing Construction) | 7.7 | GL11 | Marshall's Trading |  | 1 | 426.55 |  | 426.55 |  | Yes | M |  |  |  |  | 7.76 |  | First Floor Walls | 7 | Carpentry
2022-08-11 | Funds Transfer for Construction | 1.11 | Xfer | Marcia & Sievewright |  | 1 | 36400 | -113.75 | 36286.25 |  | Yes | X | [6 empty] | Administrative | 1 | Transfers
2022-08-16 | Deposit on building of Front Gates (To Desmond for Bejamin Wise) | 9.1 | GL11 | Bengamin Wise |  | 1 | 2000 |  | 2000 |  | Yes | L |  |  |  |  | 9.11 |  | Exterior Ground | 9 | 0
2022-08-17 | Supply and installation of bathroom vanity countertops (100 %) | 7.7 | GL19 | Modern Builders (Marlon) |  | 1 | 2615 |  | 2615 |  | Inv | L |  | MB22081701 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-17 | Fabrication of vanity doors and closet drawer faces | 7.7 | GL19 | Modern Builders (Marlon) |  | 1 | 1390 |  | 1390 |  | Inv | L |  | MB22081701 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-17 | Fabrication of external handrail for Ground floor Terrace (42 ft @ $70/ ft) | 7.7 | GL19 | Modern Builders (Marlon) |  | 1 | 2940 |  | 2940 |  | Inv | L |  | MB22081701 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-17 | Fabrication of external handrail for First floor Terrace (45 ft @ $70/ ft ) + (4 columns @ $55 / ech) | 7.7 | GL19 | Modern Builders (Marlon) |  | 1 | 3370 |  | 3370 | 10315 | Yes | L |  | MB22081701 |  |  | 7.725 |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-22 | BL&P | 8.04 | GL11 | BL&P |  | 1 | 29.66 |  | 29.66 |  | Yes | U |  |  |  |  | 8.0425 |  | Administrative | 8 | Administrative
2022-08-24 | Parts for carport fencing | 9.2 | EH0 | Fenceit |  | 1 | 474.63 |  | 474.63 |  | Yes | M |  |  |  |  | 9.229 |  | Fixtures & Fittings | 9 | 0
2022-08-25 | Deck screws for bannisters | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 35.25 |  | 35.25 |  | Inv | M |  | MB08252022 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-25 | Treated Pine for Bannisters | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 118.65 |  | 118.65 |  | Inv | M |  | MB08252022 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-25 | Lumber for Banisters | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 346.72 |  | 346.72 |  | Inv | M |  | MB08252022 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-25 | Treated Pine for Bannisters | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 66.75 |  | 66.75 |  | Inv | M |  | MB08252022 |  |  |  |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-25 | Honduras Pine | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 158.3 |  | 158.3 | 1068.01 | Yes | M |  | MB08252022 |  |  | 7.5127 |  | Wardrobes, Vanities & laundry Units | 7 | Carpentry
2022-08-25 | Fabrication of internal stair handrails (49ft @ $70/ ft ) + (4 columns @ $55 / each) | 7.51 | FF13 | Modern Builders (Marlon) |  | 1 | 3870 |  | 3870 |  | Inv | L |  | MB22082501 |  |  |  |  | Interior Outfittings and Schedules Design | 7 | Carpentry
2022-08-25 | Toilets return and pickup | 10.38 | GL11 | Barbados Steel Works |  | 1 | 255 |  | 255 |  | Yes | M |  |  |  |  | 10.3828 |  | Fixtures & Fittings | 10 | Plumbing
2022-08-25 | Transportation for toilets | 10.38 | GL11 | Ryan Thompson |  | 2 | 70 |  | 140 |  | Yes | U |  |  |  |  | 10.3828 |  | Administrative | 10 | Plumbing
2022-08-25 | Supply and installation of laundry cupboard countertop (100 %) | 7.7 | GL11 | Modern Builders (Marlon) |  | 1 | 880 |  | 880 |  | Inv | L |  | MB22082501 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-08-25 | Building kitchen cupboards (90% complete) | 7.7 | GL11 | Modern Builders (Marlon) |  | 1 | 1548 |  | 1548 |  | Inv | L |  | MB22082501 |  |  |  |  | Kitchen & Pantry Cupboards | 7 | Carpentry
2022-08-25 | Tiling internal stairs | 25.1 | GL11 | Modern Builders (Marlon) |  | 1 | 2430 |  | 2430 |  | Inv | L |  | MB22082501 |  |  |  |  | Tiling | 25 | Tiling
2022-08-25 | Tiling external steps and landing fronm kitchen and terrace | 25.1 | GL11 | Modern Builders (Marlon) |  | 1 | 760 |  | 760 | 9488 | Yes | L |  | MB22082501 |  |  | 25.135 |  | Tiling | 25 | Tiling
2022-08-25 | MISC (Charles Rowe Bridge Disc Hardware) 6/22/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 29.4 |  | 29.4 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Xclusive Products 8/25/2022 Invoice # 16676 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 101.64 | 17.787 | 119.427 | 1605.64 | Yes | M |  | MBmiscBills | 13.485 |  |  | 13 | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Misc Electrical Supplies (A F Electrical) 5/8/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 184.13 |  | 184.13 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | MISC (Charles Rowe Bridge Disc Hardware) 3/18/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 89.57 |  | 89.57 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Precision Electical Sales 376091 3/16/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 75.55 |  | 75.55 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Misc Electrical Supplies (A F Electrical) 4/7/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 51.17 |  | 51.17 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Emtage Electic (7/22/22) | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 60 |  | 60 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Misc Electrical Supplies (A F Electrical) 8/12/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 190.8 |  | 190.8 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Misc Electrical Supplies (A F Electrical) 8/12/22 | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 453.21 |  | 453.21 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | HB Hardware (Misc Elec Supplies) | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 352.38 |  | 352.38 |  | Inv | M |  | MBmiscBills |  |  |  |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-08-25 | Electrical Supplies | 13.4 | GL18 | Modern Builders (Marlon) |  | 1 | 342.34 |  | 342.34 |  | Inv | M |  | MB08252022 |  |  |  |  | Electrical Work (Outlet and switch boxes rough-ins) | 13 | Electrical
2022-09-01 | Arawak Cement | 3.06 | SL5 | Carter & Company |  | 1 | 84.27 |  | 84.27 |  | Yes | M |  |  |  |  | 3.069 |  | Guard Wall Extras | 3 | Masonary
2022-09-03 | Gang Plates | 13.4 | GL11 | All Phase Electric |  | 1 | 327.1 |  | 327.1 |  | Yes | M |  |  |  |  | 13.495 |  | Electrical Work (First Fix installation at all levels) | 13 | Electrical
2022-09-03 | Oak Wood Cream Rustic | 25.1 | GL11 | Tile Hut |  | 1 | 74.59 |  | 74.59 |  | Yes | M |  |  |  |  | 25.11 |  | Tiling | 25 | Tiling
2022-09-03 | Blanco LF BR | 25.1 | GL11 | Terrific Tiles |  | 1 | 38.25 |  | 38.25 |  | Yes | M |  |  |  |  | 25.1105 |  | Tiling | 25 | Tiling
2022-09-06 | Provisions for future HVAC | 4.1 | GL10 | Modern Builders (Marlon) |  | 1 | 1275 |  | 1275 |  | Inv | L |  | MB22090601 |  |  |  |  | HVAC | 4 | HVAC
2022-09-06 | BWA Payment | 8.04 | GL11 | BWA |  | 1 | 74.23 |  | 74.23 |  | Yes | U |  |  |  |  | 8.041 |  | Administrative | 8 | Administrative
2022-09-06 | Fabrication of kitchen cupboard countertop | 7.7 | GL11 | Modern Builders (Marlon) |  | 1 | 4815 |  | 4815 |  | Inv | L |  | MB22090601 |  |  |  |  | Kitchen Cabinet Draws & Doors | 7 | Carpentry
2022-09-06 | Electrical circuit wiring (85 % complete) | 13.4 | GL11 | Modern Builders (Marlon) |  | 1 | 3353 |  | 3353 | 12513 | Yes | L |  | MB22090601 |  |  | 13.414 |  | Electrical Work (Circuit Wiring) | 13 | Electrical
2022-09-06 | Plumbing - External works | 10.38 | GL18 | Modern Builders (Marlon) |  | 1 | 660 |  | 660 |  | Inv | L |  | MB22090601 |  |  |  |  | Plumbing | 10 | Plumbing
2022-09-06 | Plumbing - underground water tank | 10.38 | GL18 | Modern Builders (Marlon) |  | 1 | 800 |  | 800 |  | Inv | L |  | MB22090601 |  |  |  |  | Plumbing | 10 | Plumbing
2022-09-06 | Plumbing - Hot and cold water installation | 10.38 | GL18 | Modern Builders (Marlon) |  | 1 | 1610 |  | 1610 |  | Inv | L |  | MB22090601 |  |  |  |  | Plumbing | 10 | Plumbing
2022-09-06 | Funds Transfer | 1.11 | Xfer | Sievewright Rogers |  | 1 | 12000 | -37.5 | 11962.5 |  | Yes | X |  |  |  |  | 25.1105 |  | Administrative | 1 | Transfers
2022-09-08 | Pedastal Sink | 10.38 | GL11 | Barbados Steel Works |  | 1 | 133 |  | 133 |  | Yes | M |  |  |  |  | 10.385 |  | Fixtures & Fittings | 10 | Plumbing
2022-09-10 | Fencing Install | 9.1 | EH0 | Ryan Thompson |  | 1 | 210 |  | 210 |  | Yes | L |  |  |  |  | 9.11 |  | Guard Wall Extras | 9 | 0
2022-09-12 | Window Caulking (6) | 3.7 | FF15 | Meridian Windows |  | 1 | 176.25 |  | 176.25 |  | Yes | M |  |  |  |  | 3.725 |  | windows | 3 | Masonary
2022-09-12 | Window Caulking (3) | 3.7 | FF15 | Meridian Windows |  | 1 | 88.13 |  | 88.13 |  | Yes | M |  |  |  |  | 3.74 |  | windows | 3 | Masonary
2022-09-12 | Misc | 25.1 | GL11 | Marshall's Trading |  |  | 130.5 |  | 0 |  | Yes | M |  |  |  |  | 25.135 |  | Water Tank | 25 | Tiling
2022-09-12 | Scaffolding Rentals | 7.9 | GL18 | Williams Equiptment |  | 1 | 277.3 |  | 277.3 |  | Yes | U |  |  |  |  | 7.92 |  | Administrative | 7 | Carpentry
2022-09-12 | Misc Electrical | 13.4 | GL18 | Williams Electrical |  | 1 | 281.84 |  | 281.84 |  | Yes | M |  |  |  |  | 13.43 |  | Electrical Work (Circuit Wiring) | 13 | Electrical
2022-09-13 | Toilet Rental | 8.04 | EH0 | Infra Rentals |  | 1 | 305.5 |  | 305.5 |  | Yes | U |  |  |  |  | 8.0415 |  | Administrative | 8 | Administrative
2022-09-29 | Water Supply | 8.04 | GL11 | BWA |  |  | 81.7 |  | 0 |  | Yes | U |  |  |  |  | 8.0445 |  | Administrative | 8 | Administrative
2022-10-01 | Inside Trowel Plastering | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 5500 |  | 5500 |  | Yes | L |  |  |  |  | 26.525 |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-03 | Cement & Nails | 3.8 | FF13 | Carter & Company |  | 1 | 84.38 |  | 84.38 |  | Yes | M | Out of Pocket (Greg) |  |  |  | 3.83 |  | Guard Wall Extras | 3 | Masonary
2022-10-03 | Trowel Plastic supply | 26.52 | SL 17 | Trowel Plastic |  | 1 | 1284.96 |  | 1284.96 |  | Yes | M |  |  |  |  | 26.5255 |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-08 | Funds Transferred (from FCIB acct) | 1.11 | Xfer | Marcia Rogers |  | 1 | 7500 |  | 7500 |  | Yes | X |  |  |  |  | 26.5255 |  | Administrative | 1 | Transfers
2022-10-10 | Misc Refunds to Desm0nd | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 42.63 |  | 42.63 |  | Inv | M |  | DH10102020 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-10 | Misc Refunds to Desm0nd | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 236.48 |  | 236.48 |  | Inv | M |  | DH10102020 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-10 | Misc Refunds to Desm0nd | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 275.26 |  | 275.26 | 554.37 | Yes | M |  | DH10102020 |  |  | 26.5225 |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-10 | Misc Refunds to Desm0nd | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 459.24 |  | 459.24 |  | Yes | M |  |  |  |  | 26.523 |  | Painting (Finishes & Trim) | 26 | Painting
2022-10-11 | Clean Supplies Shipment Fees | 26.2 | FF13 | Massey Trading |  | 1 | 116.61 |  | 116.61 |  | Yes | U | Out of Pocket (Greg) |  |  |  | 26.245 |  | Administrative | 26 | Painting
2022-10-14 | Tile Cement reimbursment | 25.15 | FF13 | Precision Electrical |  | 1 | 62 |  | 62 |  | Yes | M | Out of Pocket (Greg) |  |  |  | 25.1525 |  | Tiling | 25 | Tiling
2022-10-14 | Barbados Customs & Exercise Fees | 26.2 | FF13 | Barbados Customs & Exercise |  | 1 | 10 |  | 10 |  | Yes | U | Out of Pocket (Greg) |  |  |  | 26.25 |  | Administrative | 26 | Painting
2022-10-15 | Cleaning Supplies | 26.2 | FF13 | Carter & Company |  | 1 | 23.62 |  | 23.62 |  | Yes | U | Out of Pocket (Greg) |  |  |  | 26.22 |  | Administrative | 26 | Painting
2022-10-21 | # 12 AWG Red/Black/Greek rolls | 13.3 | GL18 | All Phase Electric |  | 3 | 275.79 | 144.7897 | 972.1598 |  | Yes | M | Out of Pocket (Greg) |  |  |  | 13.31 |  | Electrical Work (Conduit extensions) | 13 | Electrical
2022-10-22 | Moulding for Doors | 7.7 | FF13 | Carter & Company |  | 1 | 893.66 |  | 893.66 |  | Yes | M |  |  |  |  | 7.715 |  | Fixtures & Fittings | 7 | Carpentry
2022-10-24 | Carters (Diff from door exchange) | 7.7 | FF13 | Carters |  | 1 | 72.49 |  | 72.49 |  | Yes | M |  |  |  |  | 7.74 |  | Interior Outfittings and Schedules Design | 7 | Carpentry
2022-10-25 | Mixer USE final | 3.8 | FF13 | Brian Hinds |  | 1 | 700 |  | 700 |  | Yes | U |  |  |  |  | 3.85 |  | Concrete | 3 | Masonary
2022-10-25 | BL&P | 8.04 | GL11 | BL&P |  | 1 | 70.21 |  | 70.21 |  | Yes | U |  |  |  |  | 8.0435 |  | Administrative | 8 | Administrative
2022-10-25 | Donation from Wilma | 1.11 | Xfer | Wilma Roberts |  | 1 | 2000 |  | 2000 |  | Yes | X |  |  |  |  | 7.74 |  | Administrative | 1 | Transfers
2022-10-26 | BL&P | 8.04 | GL11 | BL&P |  | 1 | 29.66 |  | 29.66 |  | Yes | U |  |  |  |  | 8.0455 |  | Administrative | 8 | Administrative
2022-10-29 | Indoor Bath and Bed door knobs | 7.7 | FF13 | Carter & Company |  | 1 | 43.33 |  | 43.33 |  | Yes | M | Out of Pocket (Greg) |  |  |  | 7.735 |  | Interior Outfittings and Schedules Design | 7 | Carpentry
2022-10-29 | Misc Supplies | 26.2 | FF13 | H&B Hardware & Lumber |  | 1 | 21.22 |  | 21.22 |  | Yes | M | Out of Pocket (Greg) |  |  |  | 26.24 |  | Fixtures & Fittings | 26 | Painting
2022-10-31 | BL&P | 8.04 | GL11 | BL&P |  | 1 | 1.05 |  | 1.05 |  | Yes | U |  |  |  |  | 8.046 |  | Administrative | 8 | Administrative
2022-11-03 | Scaffolding for final work | FF19 | 26.52 | Williams Equiptment |  | 1 | 166.85 |  | 166.85 |  | Yes | U |  |  |  |  | 26.5265 |  | Exterior Gardens & Pavement Extras | #VALUE! | #VALUE!
2022-11-11 | Partial payment for gate building | 9.1 | GL11 | Bengamin Wise |  | 1 | 520 |  | 520 |  | Yes | L |  |  |  |  | 9.11 |  | Guard Wall Extras | 9 | 0
2022-11-14 | First floor cabinet painting | FF19 | 26.52 | Desmond (Harclyde Bedford) |  | 1 | 3200 |  | 3200 |  | Inv | L |  | DH11142022 |  |  |  |  | Painting Kitchen Cabinet Draws & Doors | #VALUE! | #VALUE!
2022-11-14 | Master Bath cabinet painting | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 2500 |  | 2500 | 5700 | Yes | L |  | DH11142022 |  |  | 26.522 |  | Painting Kitchen Cabinet Draws & Doors | 26 | Painting
2022-11-25 | Final payment for gate building | 9.1 | GL11 | Bengamin Wise |  |  | 720 |  | 0 |  |  | L |  |  |  |  | 9.11 |  | Guard Wall Extras | 9 | 0
2022-12-17 | Misc Painting Supplies #810055710 (10/21/22) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 210.48 | 36.83 | 247.31 |  |  | M |  | DH12172022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-12-17 | Misc Painting Supplies #830041598 (10/25/22) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 47.8 | 8.37 | 56.17 |  |  | M |  | DH12172022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-12-17 | Misc Painting Supplies & bolts for Gate #870037068 (11/1/22) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 149.5 | 26.16 | 175.66 |  |  | M |  | DH12172022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-12-17 | Misc Painting Supplies #820050243 (12/6/22) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 248.11 | 43.42 | 291.53 |  |  | M |  | DH12172022 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2022-12-19 | Venitian blinds for Mbedroom | 26.52 | GL10 | Kooyman |  | 1 | 87.96 |  | 87.96 |  |  | M | Out of Pocket (Greg) | [5 empty] | Administrative | 26 | Painting
2022-12-21 | Solid Door (Apt/Main home) | 26.52 | GL10 | Kooyman |  | 1 | 238.29 |  | 238.29 |  |  | M | Out of Pocket (Greg) | [5 empty] | Subfloor Walls | 26 | Painting
2022-12-24 | Hot Water for home (Solar Dynamics) | 26.52 | GL10 | Kooyman |  | 1 | 3959.99 |  | 3959.99 |  |  | M | Out of Pocket (Greg) | Kooy122422 |  |  |  |  | Interior Outfittings and Schedules Design | 26 | Painting
2022-12-24 | Misc Purchases (masking tape etc) | 26.52 | GL10 | Kooyman |  | 1 | 46.96 |  | 46.96 |  |  | M | Out of Pocket (Greg) | Kooy122422 |  |  |  |  | Administrative | 26 | Painting
2022-12-24 | Curtain rods & Misc | 26.52 | GL10 | Kooyman |  | 1 | 105.97 |  | 105.97 |  |  | M | Out of Pocket (Greg) | [5 empty] | Administrative | 26 | Painting
2022-12-24 | Curtain rods & Misc | 26.52 | GL10 | Kooyman |  | 1 | 89.99 |  | 89.99 |  |  | M | Out of Pocket (Greg) | [5 empty] | Administrative | 26 | Painting
2022-12-24 | PVC blinds | 26.52 | GL10 | Kooyman |  | 1 | 124.97 |  | 124.97 |  |  | M | Out of Pocket (Greg) | [5 empty] | Administrative | 26 | Painting
2023-01-05 | Burgular Bars for Gym | 26.52 | GL10 | Andy Osbourne |  | 1 | 370 |  | 370 |  |  | M | out of Pocket (Greg) | [6 empty] | 26 | Painting
2023-01-05 | Burgular Bars for Gym | 26.52 | GL10 | Andy Osbourne |  | 1 | 300 |  | 300 |  |  | M | Out of Pocket (Greg) | [5 empty] | Windows | 26 | Painting
2023-02-21 | Painting Doors & Jams | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 26 | 250 |  | 6500 |  |  | L |  | Des02212023 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2023-02-21 | Painting Handrails | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 1800 |  | 1800 |  |  | L |  | Des02212023 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2023-02-21 | Misc Painting Suppplies | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 378.12 |  | 378.12 |  |  | M |  | Des02212023 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2023-12-14 | Installation of Potable Water Tank | 10.38 | GL18 | Desmond Holder |  | 1 | 750 |  | 750 |  |  | L | Out of Pocket (Greg) | DesHol |  |  |  |  | Plumbing | 10 | Plumbing
2/21//23 | Doors Installation (Interior) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 11 | 125 |  | 1375 |  |  | L |  | Des02212023 |  |  |  |  | Painting (Finishes & Trim) | 26 | Painting
2/21//23 | Misc Supplies (Saw Blades) | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 26.2 |  | 26.2 |  |  | M | out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Refer to invoice 216 dated 11/10/22 (Sean Granison_Oct 2022.pdf) On Time Freight & Construction | 5.67 | GL11 | Shawn Grandison |  |  | 11250 |  | 0 |  |  | L |  |  |  |  | 5.671 |  | Exterior Ground | 5 | Earthworks
2/21//23 | Jacuzzi and Shower Doors | 26.52 | GL10 | Platinum Imports |  |  |  |  | 0 |  |  | M | Out of Pocket (Greg)
2/21//23 | Misc Supplies | 26.52 | GL10 | Desmond (Harclyde Bedford) |  | 1 | 426.94 |  | 426.94 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Doors | 26.52 | GL10 | Carters |  | 1 | 0 |  | 0 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Gas Installation | 26.52 | GL10 | Rubis |  | 1 | 0 |  | 0 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Port Fees | 26.52 | GL10 | Blue Waters |  | 1 | 0 |  | 0 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Container transportation and unstuffing Fees | 26.52 | GL10 | Hank |  | 1 | 0 |  | 0 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
2/21//23 | Shipping Brooker Fee | 26.52 | AA1 | Lewellan Tull |  | 1 | 0 |  | 0 |  |  | M | Out of Pocket (Greg) | [6 empty] | 26 | Painting
PostIT